## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10038 | New | Providing FHTC from existing distribution system as per specification for Dekhlapara PWSS. | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000326/2023-2024 | 2423/ALD | 09/11/2023 | 08/01/2024 | SHYAMAL ROY | 7.21 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Alipurduar Division | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10038 | New | CONS. FOR RESERVOIR (200 M3), RISING MAIN AND DISTRIBUTION LINE FOR DHEKLAPARA MAIN DIVISION CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000030/2022-2023 | 284/ALD | 26/04/2022 | 23/09/2022 | SUBHAS CHANDRA ROY | 86.68 | 70.85 | 81.74 | 100
3 | ALIPURDUAR | Madarihat | Alipurduar Division | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10038 | New | New service connection charges for Dheklapara T.G PWSS P/H no-I (Cha Sundari) |  |  | BILL/00489/2024-2025 | 325/24-25/PFMS | 02/12/2024 | 02/12/2024 | WBSEDCL | 5.04 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Alipurduar Division | Dheklapara Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10038 | New | CONS. OF STORAGE TANK, BOUNDARY WALL, PUMP HOUSE, TUBE WELL (1 No.), RISING MAIN AND LAND DEVELOPMENT FOR NEPANIA MAIN DIVISION (150 Unit) CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000032/2022-2023 | 296/ALD | 27/04/2022 | 01/01/2026 | S.N. POLYMERS PRIVATE LIMITED | 108.37 | 0 | 0 | 75
Total | [13 empty] | 207.3 | 70.85 | 34.18