## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 | New | New Connection for Toorsa TG Zone-I Phase-II |  |  | BILL/00032/2022-2023 | 357/22-23/PFMS | 12/12/2022 | 12/12/2022 | WBSEDCL | 1.19 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 | New | New Connection for Torsa TG Zone-II Phase-I |  |  | BILL/00033/2022-2023 | 358/22-23/PFMS | 12/12/2022 | 12/12/2022 | WBSEDCL | 1.19 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 | New | New Connection for Torsa TG Zone-II |  |  | BILL/00034/2022-2023 | 359/22-23/PFMS | 12/12/2022 | 12/12/2022 | WBSEDCL | 1.19 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 | New | CONS. OF RESERVOIR (100M3), BOUNDARY WALL (80m), PUMP HOUSE (1No.), TUBE WELL (2 Nos.), RISING MAIN AND LAND DEVELOPMENT FOR TORSHA (Hat Khola Line, Naya Line, 3 No. Line (A) AND (B) and Khoyar line) 256 unit CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000028/2022-2023 | 282/ALD | 26/04/2022 | 23/09/2022 | DILIP MAHATO | 104 | 103.66 | 99.67 | 88
5 | ALIPURDUAR | Kalchini | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 | New | Soil investigation work for Cha Sundori Project at 4 different places of Torsha TG & Dekhlapara TG within Alipurduar District under Alipurduar Division PHE Dte. | Birpara A.E |  | ORD/000448/2021-2022 | 2655/ALD | 21/02/2022 | 23/03/2022 | M/S HAZRA CONSTRUCTION | 4.9 | 4.9 | 100 | 87
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component for Torsa TG Sawa Line, Chhetri Line, Gopa Line, Jiten Line 220 unit cha Sundari Water Supply Scheme , Zone-II ,P.H No.- I and II under NMD-II ,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000732/2022-2023 | 70/NMD-II | 09/01/2023 | 08/02/2023 | SARKAR ELECTRIC | 26.05 | 26.05 | 100 | 100
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component for Torsa TG [Hatkhola Line,Naya Line, 3 no. Line (A) Khoyar Line ] 256 unit cha Sundari Water Supply Scheme , Zone-I ,P.H No.-IandIIunder NMD-II ,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000733/2022-2023 | 71/NMD-II | 09/01/2023 | 08/02/2023 | B.B CONCERNED | 26.05 | 26.05 | 100 | 87
8 | ALIPURDUAR | Kalchini | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 | New | New Connection for Torsa TG Zone-I Phase-I |  |  | BILL/00035/2022-2023 | 360/22-23/PFMS | 12/12/2022 | 12/12/2022 | WBSEDCL | 1.19 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 | New | Providing FHTC from existing distribution system as per specification for Torsha Cha Sundari PWSS PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000268/2023-2024 | 1886/ALD | 07/09/2023 | 07/10/2023 | D. K. & SONS | 1.01 | 0 | 0 | 100
10 | ALIPURDUAR | Kalchini | Alipurduar Division | Torsha Tea Garden Area Piped Water Supply Scheme in relation with Chaa Sundari Project. | SM/10039 | New | CONS. OF RESERVOIR (100M3), BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND LAND DEVELOPMENT FOR TORSHA (Sawa Line, Chetri Line, Bancha Line,Gopal Line, Jiten Line)220 unit CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000029/2022-2023 | 283/ALD | 26/04/2022 | 20/02/2023 | MAHENDRA CHHETRI | 100.66 | 97.34 | 96.71 | 86
Total | [13 empty] | 267.41 | 258 | 96.48