## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Gap filling in laying distribution system by making culvert crossing and laying of DI and UPVC pipes under Narathali Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) |  |  | ORD/000317/2022-2023 | 2226/ALD | 21/11/2022 | 05/01/2023 | MADHAB SAHA | 4.65 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Gap filling in laying distribution system by making culvert crossing and laying of DI and UPVC pipes under Narathali Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) |  |  | ORD/000318/2022-2023 | 2227/ALD | 21/11/2022 | 05/01/2023 | HARI CONSTRUCTION | 3.45 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Restoration of Laying distribution system by replacing of damaged AC pipeline with UPVC pipeline and constructon of boundary wall, toilet and repairing of pump house (2nd site) at Narathali Water Supply Scheme under Alipurduar Division, PHE Dte | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000183/2021-2022 | 1312/ALD | 05/10/2021 | 04/12/2021 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 11.97 | 3.92 | 32.76 | 69
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Construction of Pump House ,Boundary Wall and Tube well Boring by ODEX-165 Method of drilling including Rising Main for NARATHALI PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000410/2021-2022 | 2526/ALD | 11/02/2022 | 12/05/2022 | TAPAN CHANDA | 41.03 | 27.14 | 66.14 | 70
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Laying of distribution of UPVC pipeline including FHTC for KHOARDANGA AREA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000437/2021-2022 | 2743/ALD | 24/02/2022 | 25/04/2022 | HARIDAS GHOSH | 87.82 | 87.69 | 99.86 | 99
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Laying of distribution of UPVC pipeline including FHTC for MADHYA NARATHALI AREA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000438/2021-2022 | 2744/ALD | 24/02/2022 | 25/04/2022 | DAS CONSTRUCTION | 87.58 | 66.41 | 75.83 | 68
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Laying of distribution of UPVC pipeline including FHTC for PASCHI NARATHALI MOUZA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000436/2021-2022 | 2742/ALD | 24/02/2022 | 25/04/2022 | MADHAB SAHA | 87.55 | 74.91 | 85.56 | 71
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Laying of distribution of UPVC pipeline including FHTC for NARATHALI MOUZA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000439/2021-2022 | 2745/ALD | 24/02/2022 | 25/04/2022 | SASANKA ROY | 87.59 | 78.42 | 89.54 | 70
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Laying of pipeline at PASCHIM NARATHALI by extension of pipeline from Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000440/2021-2022 | 2746/ALD | 24/02/2022 | 25/04/2022 | AKANSHA COMMERCIAL PRIVATE LTD. | 93.92 | 58.61 | 62.4 | 64
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Narthali Water Supply Scheme TW No.-V under NMD-II, PHE. Dte, Alipurduar. |  |  | ORD/000914/2021-2022 | 405/NMD-II | 22/03/2022 | 21/04/2022 | HARAGOURI ENTERPRISE | 2.38 | 2.38 | 100 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Renovation of the electrical installation of NARARTHALI W/S scheme P/H No. I under NMD-II , PHE, Dte. Alipurduar . |  |  | ORD/000830/2022-2023 | 494/NMD-II | 02/03/2023 | 17/03/2023 | SARKAR ELECTRIC | 1.09 | 0 | 0 | 0
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Providing extension of distribution line, repair of water pipeline in 10/142 booth at Khoardanga 2 G.P from the commissioned NARATHALI PWSS (UID-APD-166) UNDER ALIPURDUAR DIVISION PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000309/2020-2021 | 1483/ALD | 27/01/2021 | 28/03/2021 | TAPASH DAS | 15.73 | 1.42 | 9.01 | 70
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Construction of boundary wall, repairing of pump house of 3rd T/W site and interconnection between 2nd and 3rd site by using DI pipe with pillar including supply of CI materials at Narathali Water Supply Scheme under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000075/2021-2022 | 881/ALD | 03/09/2021 | 02/11/2021 | SREE MAA CONSTRUCTION & CO. | 13.19 | 8.13 | 61.68 | 71
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Construction of 550cum OHR for Augmentation of Narathali Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000408/2021-2022 | 2524/ALD | 11/02/2022 | 10/08/2022 | TAPAN CHANDA | 98.12 | 89.52 | 91.23 | 72
15 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Narthali Water Supply Scheme TW No.- IV under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000907/2021-2022 | 437/ NMD-II | 29/03/2022 | 28/04/2022 | ASHOKE ADHIKARY | 7.85 | 7.33 | 93.44 | 71
16 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Narthali Water Supply Scheme TW No. - V under NMD-II, PHE Dte., Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000001/2022-2023 | 473/NMD-II | 07/04/2022 | 07/05/2022 | M/S PARITOSH BHOWMICK & CO. | 7.85 | 7.85 | 100 | 100
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | "Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. (for the financial year 2022-2023 from 01/04/2022 onwards)" | Birpara A.E | Birpara Sub Division | ORD/000578/2021-2022 | 3223/ALD | 31/03/2022 | 31/03/2023 | DILIP MAHATO | 4.96 | 3.06 | 61.82 | 53.5
18 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Narthali Water Supply Scheme TW No.-IV under NMD-II,PHE.Dte, Alipurduar. |  |  | ORD/000912/2021-2022 | 403/NMD-II | 22/03/2022 | 21/04/2022 | RMD TRADING | 2.39 | 2.39 | 100 | 100
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Narathali Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000108/2022-2023 | 700/ALD | 08/06/2022 | 08/07/2022 | M/S SHIB RATAN BHOWMICK & CO | 4.88 | 4.88 | 100 | 70
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 716/ALD | 13/06/2022 |  | Resource Division | 51.21 | 0 | 0 | 0
21 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | NARATHALI T/W no.V, Alipurduar II, Application no. 4002930550, Ref no. 402824235, SM/10154/159 |  |  | VCH/000696/2022-2023 | BP-24/22-23 | 15/07/2022 |  | WBSEDCL | 0.87 | 0 | 0 | 0
22 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | NARATHALI T/W no.IV, Alipurduar II, Application no. 4002930565, Ref no. 402824639, SM10154/159 |  |  | VCH/000697/2022-2023 | BP-25/22-23 | 15/07/2022 |  | WBSEDCL | 0.87 | 0 | 0 | 0
23 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF NARATHALI PIPED WATER SUPPLY SCHEME | SM/10154 | Augmentation | Laying of distribution of UPVC pipeline including FHTC for KHOARDANGA AREA under NARATHALI PWSS under Alipurduar Division, PHE DTE 2743/ALD DT:24/02/2022 |  |  | BILL/00599/2023-2024 | 447/23-24/PFMS | 30/03/2024 |  | HARIDAS GHOSH | 1.98 | 0 | 0 | 0
Total | [13 empty] | 718.92 | 524.07 | 72.9