## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME | SM/10155 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Totpara WSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Madarihat - Birpara Block | ORD/000283/2021-2022 | 1852/ALD | 13/12/2021 | 12/01/2022 | HARI CONSTRUCTION | 5.04 | 5.04 | 100 | 96
2 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME | SM/10155 | Augmentation | Restoration of Laying Distribution system by replacing damaged AC pipeline with DI and UPVC pipe for TATPARA WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000498/2021-2022 | 3003/ALD | 15/03/2022 | 14/05/2022 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 39.2 | 37.8 | 96.42 | 98
3 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME | SM/10155 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Totpara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Birpara A.E | RWS Madarihat - Birpara Block | ORD/000112/2022-2023 | 704/ALD | 08/06/2022 | 08/07/2022 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.92 | 4.92 | 100 | 99
4 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME | SM/10155 | Augmentation | Laying Distribution pipe with DI pipe with pillar of TATPARA WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000532/2021-2022 | 3106/ALD | 24/03/2022 | 23/05/2022 | HARI CONSTRUCTION | 7.06 | 6.94 | 98.25 | 98
5 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME | SM/10155 | Augmentation | Construction of 250cum OHR for TATPARA Piped Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000441/2021-2022 | 2749/ALD | 24/02/2022 | 23/08/2022 | M/S DUTTA AND CO | 57.62 | 42.05 | 72.98 | 99
6 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME | SM/10155 | Augmentation | Repairing and renovation of 2 nos. pump house, boundary wall (H/W Site, 2nd site), Pathway, Cons. Of 2 nos New Toilet and restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipe at Totpara Water Supply Scheme under Alipurduatr Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E | Alipurduar Sub Division,RWS Madarihat - Birpara Block | ORD/000238/2021-2022 | 1579/ALD | 22/11/2021 | 06/03/2025 | NARENDRA BHADANI. | 22.78 | 19.7 | 86.48 | 100
7 | ALIPURDUAR |  | Alipurduar Division | REJUVENATION OF TATPARA PIPED WATER SUPPLY SCHEME | SM/10155 | Augmentation | Repairing and renovation of 2 nos. pump house, boundary wall (H/W Site, 2nd site), Pathway, Cons. Of 2 nos New Toilet and restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipe at Totpara Water Supply Scheme under Alipurduatr Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E | Alipurduar Sub Division,RWS Madarihat - Birpara Block | ORD/000239/2021-2022 | 1580/ALD | 22/11/2021 | 06/03/2025 | SASANKA ROY | 22.78 | 20.11 | 88.26 | 100
Total | [13 empty] | 159.41 | 136.56 | 85.67