## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Jateswar PWSS under Alipurduar Division, PHE Dte. Part-4 | Birpara A.E | Alipurduar Sub Division | ORD/000118/2022-2023 | 411/ALD | 11/05/2022 | 25/06/2022 | SOUVIK ROY PALADHI | 24.47 | 10.14 | 41.43 | 63
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Jateswar PWSS under Alipurduar Division, PHE Dte. Part-5 | Birpara A.E | Alipurduar Sub Division | ORD/000119/2022-2023 | 412/ALD | 11/05/2022 | 25/06/2022 | AASHIRBAD ENTERPRISE | 24.1 | 0 | 0 | 65
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Construction of 450cum OHR for Bhutnirghat Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000310/2021-2022 | 2186/ALD | 11/01/2022 | 10/07/2022 | DILIP MAHATO | 87.59 | 12.6 | 14.39 | 80
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 2107/ALD | 09/11/2022 | 09/11/2022 | Resource Division | 10.92 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Sahapara and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000539/2021-2022 | 3191/ALD | 28/03/2022 | 27/05/2022 | AASHIRBAD ENTERPRISE | 12.35 | 10.78 | 87.25 | 78
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Construction of 500cum OHR for Augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000409/2021-2022 | 2525/ALD | 11/02/2022 | 10/08/2022 | ASHIT KUMAR SINGHA | 91.76 | 82.23 | 89.61 | 80
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-I | Birpara A.E | Alipurduar Sub Division | ORD/000467/2021-2022 | 2812/ALD | 28/02/2022 | 29/04/2022 | SOUVIK ROY PALADHI | 98.49 | 96.3 | 97.78 | 63
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-II | Birpara A.E | Alipurduar Sub Division | ORD/000450/2021-2022 | 2747/ALD | 24/02/2022 | 25/04/2022 | TAPASH DAS | 49.62 | 39.08 | 78.76 | 59
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-II | Birpara A.E | Alipurduar Sub Division | ORD/000451/2021-2022 | 2748/ALD | 24/02/2022 | 25/04/2022 | KAMALESH ROY | 49.62 | 47.81 | 96.35 | 63
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Beltali Road and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000026/2022-2023 | 24/ALD | 01/04/2022 | 31/05/2022 | AASHIRBAD ENTERPRISE | 12.35 | 12.33 | 99.84 | 80
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 12/06/2022 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Laying of UPVC/DI distribution pipeline including road and culvert crossing of different area for augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000195/2022-2023 | 1225/ALD | 10/08/2022 | 09/10/2022 | SOUVIK ROY PALADHI | 41.01 | 39.23 | 95.66 | 63
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Laying of UPVC/DI distribution pipeline including road and culvert crossing of different area for augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000202/2022-2023 | 1226/ALD | 10/08/2022 | 08/12/2022 | TAPASH DAS | 41.01 | 38.71 | 94.38 | 63
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 2928/ALD | 10/03/2022 | 10/03/2022 | Resource Division | 17.75 | 0 | 0 | 0
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Quotation for New Connection in Dalgaon |  |  | BILL/00108/2022-2023 | 446/22-23/PFMS | 21/01/2023 | 21/01/2023 | WBSEDCL | 0.1 | 0 | 0 | 0
16 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT JATESWAR PWSS PH NO-IV |  |  | BILL/00031/2023-2024 | BP-2023-24-21 | 27/04/2023 | 27/04/2023 | WBSEDCL | 1.34 | 0 | 0 | 0
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for JATESWAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000411/2021-2022 | 2527/ALD | 11/02/2022 | 28/10/2024 | ASHIT KUMAR SINGHA | 44.59 | 9.03 | 20.24 | 63
18 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Jateswar water supply scheme, TW no. IV and V under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000014/2023-2024 | 889/NMD-II | 02/05/2023 | 01/06/2023 | HARA PROSAD DAS | 21.7 | 0 | 0 | 60
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Providing FHTC from existing distribution system as per specification for JATESWAR PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000453/2023-2024 | 235/ALD | 17/01/2024 | 16/04/2024 | BILTU DAS | 63.54 | 0 | 0 | 0
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Sinking big dia. Tube well of 250mm X 200mm dia. Using MS slotted strainer at required depth by Reverse Rotary Method of drilling at 2nd site for Aug. of Jateswar PWSS (SM/10156) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000494/2023-2024 | 750/ALD | 12/03/2024 | 10/06/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 20.48 | 0 | 0 | 100
21 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Laying of UPVC/DI pipe line at flank of Asian Highway Road at Jateswar to towards Kazali Bazar under Jateswar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000454/2022-2023 | 2944/ALD | 20/01/2023 | 21/03/2023 | TAPASH DAS | 16.1 | 5.76 | 35.74 | 95
22 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | New Service Connection charges for Dalimpur Zone-II PH NO-II,JATESWAR |  |  | BILL/00617/2024-2025 | BP-140/24-25 | 11/06/2024 | 11/06/2024 | WBSEDCL | 4.35 | 0 | 0 | 0
23 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | New Service Connection Charges for Dalimpur Zone-II, PH NO-I Jateswar |  |  | BILL/00618/2024-2025 | BP-141/24-25 | 11/06/2024 | 11/06/2024 | WBSEDCL | 3.72 | 0 | 0 | 0
24 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JATESWAR PIPED WATER SUPPLY SCHEME | SM/10156 | Augmentation | Cons. of pump house at 2nd site, laying of UPVC pipeline for left out household connection and rising main with CIDF pipe and specials and other allied works for Augmentation of Jateswar PWSS of Birpara Sub-Division under Alipurduar Division, PHE Dte.(SM/10156) | Birpara A.E | Alipurduar Sub Division | ORD/000504/2023-2024 | 822/ALD | 14/03/2024 | 07/07/2025 | TAPASH DAS | 50.51 | 0 | 0 | 75
Total | [13 empty] | 788.45 | 403.96 | 51.24