## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Jogijhora WSS under Alipurduar Division, PHE Dte. Part-3 (2 nd call) | Birpara A.E | RWS Falakata Block | ORD/000572/2021-2022 | 3145/ALD | 25/03/2022 | 24/04/2022 | M/S SURAJIT DEY & CO | 5.02 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Providing FHTC from existing distribution system as per specification for JAGIJHORA PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000286/2023-2024 | 1993/ALD | 15/09/2023 | 14/11/2023 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 33.81 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Construction of 300cum OHR for Augmentation of Jagijhora Barabak Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000414/2021-2022 | 2582/ALD | 17/02/2022 | 16/08/2022 | ASHIM KUMAR GHOSH | 63.76 | 0 | 0 | 43
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-2 Venue: 1) Jogijhora 2)Jateswar 3)Gopalpur 4)Madhya Parokata | HQ-A.E |  | ORD/000360/2021-2022 | 2122/ALD | 05/01/2022 | 04/02/2022 | MOYTEC | 4.9 | 0 | 0 | 26
5 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT JOGOJHORA BARABAK TW NO-III |  |  | BILL/00072/2023-2024 | BP-2023-24-66 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.46 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Construction of boundary wall for Jogijhora Barabak PWSS of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/10169) | Birpara A.E | Birpara Sub Division | ORD/000509/2023-2024 | 827/ALD | 14/03/2024 | 13/05/2024 | MANI PRADHAN | 2.5 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Construction of Pump House ,Boundary Wall and Tube well Boring by ODEX-165 Method of drilling including Rising Main for JAGIJHORA BARABAK PWSS under Alipurduar Division PHE DTE | Birpara A.E | Alipurduar Sub Division | ORD/000425/2021-2022 | 2609/ALD | 17/02/2022 | 18/05/2022 | SUBHAS CHANDRA ROY | 21.13 | 0 | 0 | 100
8 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Jogijhora Barabak water supply scheme, TW no. III under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000018/2023-2024 | 907/NMD-II | 04/05/2023 | 03/06/2023 | A.K SIKDAR | 10.36 | 0 | 0 | 100
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Laying of distribution of HDPE/DI pipeline for Jogijhora Barabak PWSS under Alipurduar Division, PHE DTE. | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000477/2021-2022 | 2896/ALD | 08/03/2022 | 23/10/2024 | MS DEYS CONSTRUCTION | 56.01 | 0 | 0 | 100
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 3606/ALD | 24/10/2024 | 24/10/2024 | Resource Division | 9.11 | 0 | 0 | 0
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Laying of HDPE pipe line for left out house hold connection at Ethelbari TG PWSS(SM/13449) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000540/2023-2024 | 894/ALD | 15/03/2024 | 10/03/2025 | DILIP MAHATO | 18.65 | 0 | 0 | 100
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | LAYING OF HDPE PIPELINE FOR LEFTOUT PORTION OF FHTC AT JOGIJHORA & BHUTNIRGHAT MOUZA UNDER AUGMENTATION OF JAGIJHORA BARABAK SCHEME (SM/10169) UNDER ALIPURDUAR DIVISION, PHE DTE. | Alipurduar Sadar Sub Division,Birpara A.E | Birpara Sub Division,RWS Falakata Block | ORD/000394/2024-2025 | 4180/ALD | 03/12/2024 | 30/10/2025 | NARENDRA BHADANI. | 57.58 | 0 | 0 | 80
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Reparing of Pump House at 2nd site of Jogijhora Barabak PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000610/2024-2025 | 5600/ALD | 27/03/2025 | 26/05/2025 | NARENDRA BHADANI. | 0.79 | 0 | 0 | 0
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Reparing of Pump House at 3nd site of Jogijhora Barabak PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000614/2024-2025 | 5604/ALD | 27/03/2025 | 26/05/2025 | NARENDRA BHADANI. | 0.95 | 0 | 0 | 0
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Reparing of Pump House at 1st site of Jogijhora Barabak PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000609/2024-2025 | 5599/ALD | 27/03/2025 | 26/05/2025 | NARENDRA BHADANI. | 0.78 | 0 | 0 | 0
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Birpara A.E | RWS Falakata Block | ORD/000130/2025-2026 | 1629/ALD | 04/08/2025 | 03/10/2025 | NARENDRA BHADANI. | 18.13 | 0 | 0 | 0
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JAGIJHORA BARABAK PIPED WATER SUPPLY SCHEME | SM/10169 | Augmentation | Gap filling by DI and HDPE pipeline in Jagijhora Barabak PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division,RWS Falakata Block | ORD/000353/2023-2024 | 2605/ALD | 04/12/2023 | 31/07/2024 | MONORAMA ENTERPRISE | 9.99 | 0 | 0 | 80
Total | [13 empty] | 389.3 | 0 | 0