## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000471/2021-2022 | 2871/ALD | 07/03/2022 | 06/05/2022 | TAPAN CHANDA | 100.9 | 74.42 | 73.75 | 72
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-D) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000497/2021-2022 | 3002/ALD | 15/03/2022 | 14/05/2022 | M/S DUTTA AND CO | 95.57 | 74.72 | 78.18 | 71
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-C) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000472/2021-2022 | 2872/ALD | 07/03/2022 | 06/05/2022 | MAHENDRA CHHETRI | 94.52 | 77.53 | 82.02 | 73
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Balance work of construction of boundary wall & repairing of pump house at 2nd Tubewell site of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000483/2021-2022 | 2659/ALD | 21/02/2022 | 07/04/2022 | TAPASH KUMAR BHOWMICK | 4.49 | 3.62 | 80.7 | 73
5 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Quotation for new service connection at Uttar majherdabri W/SS TW No IV Application No-4002956335 |  |  | VCH/000692/2022-2023 | null | 04/08/2022 |  | WBSEDCL | 0.87 | 0 | 0 | 0
6 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Quotation for new service connection at uttar majherdabri W/SS TW No III Application No-4002956327 |  |  | VCH/000691/2022-2023 | null | 04/08/2022 |  | WBSEDCL | 0.87 | 0 | 0 | 0
7 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Quotation for new service connection for UTTAR MAJHER DABRI w/ss T/W no. IV. Application no. 4002956335 |  |  | VCH/001281/2022-2023 | BP-42/22-23 | 08/08/2022 |  | WBSEDCL | 0.87 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Quotation for new service connection for uttar majher Dabri w/s scheme t/W no. II , Application no. 40025956327 |  |  | VCH/001280/2022-2023 | BP-41/22-23 | 08/08/2022 |  | WBSEDCL | 0.87 | 0 | 0 | 0
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Uttar Majherdabri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000109/2022-2023 | 701/ALD | 08/06/2022 | 08/07/2022 | HARIDAS GHOSH | 4.96 | 4.96 | 100 | 73
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Uttar Majherdabri Water Supply Scheme TW No.- IV under NMD-II PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000003/2022-2023 | 475/NMD-II | 07/04/2022 | 07/05/2022 | DEB CONSTRUCTION | 7.85 | 5.8 | 73.92 | 73
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Extension of UPVC pipeline for augmentation of Uttar Majherdabri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000197/2022-2023 | 1223/ALD | 10/08/2022 | 09/10/2022 | DILIP MAHATO | 56.93 | 54.35 | 95.46 | 73
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000470/2021-2022 | 2870/ALD | 07/03/2022 | 06/05/2022 | DILIP MAHATO | 101.03 | 95.67 | 94.69 | 69
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Extension of UPVC pipeline for augmentation of Uttar Majherdabri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000198/2022-2023 | 1224/ALD | 10/08/2022 | 09/10/2022 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 46.73 | 40.43 | 86.52 | 70
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) |  |  | ORD/000413/2022-2023 | 2728/ALD | 30/12/2022 | 30/12/2023 | APSARI BHOWMICK | 4.8 | 0 | 0 | 0
15 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Uttar Majherdabri Water Supply Scheme TW No.-III under NMD-II,PHE. Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000004/2022-2023 | 532/NMD-II | 20/04/2022 | 20/05/2022 | M/S P.P ELECTRICALS | 7.82 | 5.85 | 74.72 | 69
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Construction of boundary wall (H/W) Site, Toilet, Repairing of Pump House & 125 nos. house connection of Uttar Majherdabri Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000275/2020-2021 | 1287/ALD | 05/01/2021 | 06/03/2021 | TAPASH KUMAR BHOWMICK | 20.49 | 12.7 | 61.96 | 73
17 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Uttar Majherdabri Water Supply Scheme TW No.-III under NMD-II,PHE.Dte,Alipurduar. |  |  | ORD/000928/2021-2022 | 411/NMD-II | 22/03/2022 | 21/04/2022 | QUAZI NOZRUL ISLAM | 2.39 | 2.37 | 99.03 | 0
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Providing FHTC in school in Uttar Majherdabri PWSS under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000496/2022-2023 | 3360/ALD | 14/03/2023 | 13/04/2023 | HARIDAS GHOSH | 0.22 | 0.22 | 100 | 100
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for UTTAR MAJHERDABRI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000427/2021-2022 | 2611/ALD | 17/02/2022 | 18/05/2022 | HIGHLIFE INTERNATIONAL | 44.39 | 37.06 | 83.5 | 100
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 1589/ALD | 14/09/2022 |  | Resource Division | 12.3 | 0 | 0 | 0
21 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 108/ALD | 10/01/2024 |  | Resource Division | 4.47 | 0 | 0 | 0
22 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Uttar Majherdabri Water Supply Scheme TW No.-IV under NMD-II, PHE. Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000910/2021-2022 | 0401/NMD-II | 22/03/2022 | 21/04/2022 | S P ENTERPRISE (KOLKATA) | 2.39 | 1.25 | 52.16 | 100
23 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF UTTAR MAJHER DABRI PIPED WATER SUPPLY SCHEME | SM/10171 | Augmentation | Construction of 450cum OHR for Augmentation of Uttar Majher Dabri Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000413/2021-2022 | 2581/ALD | 17/02/2022 | 07/02/2024 | M/S DUTTA AND CO | 87.59 | 51.24 | 58.51 | 99
Total | [13 empty] | 703.32 | 542.17 | 77.09