## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Entry of data of Functional Household Tap Connection (FHTC under JJM) of PWSS in Website under Alipurduar Division, PHE Dte. (Part-A) | HQ-A.E |  | ORD/000586/2021-2022 | 743/ALD | 11/08/2021 | 09/11/2021 | TAPASH KUMAR BHOWMICK | 0.96 | 0.96 | 100 | 65
2 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Supply of CIPE Special & CI Jeffy Coupling for Mathura Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000113/2022-2023 | 705/ALD | 08/06/2022 | 08/07/2022 | SASANKA ROY | 4.79 | 4.79 | 100 | 65
3 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-C) | HQ-A.E |  | ORD/000585/2021-2022 | 1969/ALD | 24/12/2021 | 24/03/2022 | TAPASH KUMAR BHOWMICK | 0.96 | 0.96 | 100 | 64
4 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Quotation for new service connection at Mathura TG P/H No-I. Application No- 4003027935 |  |  | BILL/00016/2022-2023 | BP-109/22-23 | 19/12/2022 |  | WBSEDCL | 1.34 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Construction of 400cum OHR for Mathura Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000415/2021-2022 | 2583/ALD | 17/02/2022 | 16/08/2022 | M/S SURAJIT DEY & CO | 77.51 | 58.47 | 75.44 | 63
6 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for MATHURA TG AREA PWSS Under Alipurduar Division PHE DTE | Alipurduar RWS | Birpara Sub Division | ORD/000012/2022-2023 | 22/ALD | 01/04/2022 | 30/07/2022 | TAPASH KUMAR BHOWMICK | 246.44 | 226.9 | 92.07 | 65
7 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 08/10/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MATHURA TG PWSS PH NO-II |  |  | BILL/00047/2023-2024 | BP-2023-24-9 | 20/04/2023 |  | WBSEDCL | 1.41 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 395/ALD | 11/05/2022 |  | Resource Division | 3.16 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at H/W site including laying distribution system and providing FHTC for MATHURA TG AREA PWSS Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000007/2022-2023 | 17/ALD | 01/04/2022 | 30/07/2022 | M/S SURAJIT DEY & CO | 246.1 | 119.65 | 48.62 | 69
11 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MATHURA TG water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000805/2022-2023 | 393/NMD-II | 23/02/2023 | 25/03/2023 | B.B CONCERNED | 22.77 | 21.48 | 94.34 | 100
12 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Mathura Tea Garden Area Piped Water Supply Scheme (SM-10172) of Alipurduar - I Block under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000536/2023-2024 | 852/ALD | 14/03/2024 | 13/04/2024 | GUHA ENTERPRISE | 11.62 | 5.61 | 48.22 | 75
13 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | MATHURA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10172 | New | Supply of DI Special and CI Jeffy Coupling for Mathura TG Water Supply Scheme (SM/10172) of Alipurduar-I Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000513/2023-2024 | 831/ALD | 14/03/2024 | 13/05/2024 | TAPASH KUMAR BHOWMICK | 11.6 | 5.47 | 47.11 | 50
Total | [13 empty] | 1828.67 | 444.29 | 24.3