## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Quotation for new connection of Sidahabari W/Ss P/H no-II, Application no. 4002994719, Ref: 402875931 |  |  | VCH/001422/2022-2023 | BP-70/22-23 | 30/09/2022 | 30/09/2022 | WBSEDCL | 1.75 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Quotation for new connection of Sidahabari PWSS P/H no-I, Application no. 4002994696, Ref: 402875912 |  |  | VCH/001423/2022-2023 | BP-71/22-23 | 30/09/2022 | 30/09/2022 | WBSEDCL | 1.75 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Quotation for new service connection at SIDHABARI P/H NO-II |  |  | VCH/001310/2022-2023 |  | 27/09/2022 | 27/09/2022 | WBSEDCL | 1.75 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Quotation for new service connection at SIDHABARI P/H NO-I |  |  | VCH/001311/2022-2023 |  | 27/09/2022 | 27/09/2022 | WBSEDCL | 1.75 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Construction of 250cum OHR for Sidhabari Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000418/2021-2022 | 2585/ALD | 17/02/2022 | 16/08/2022 | MS CTR CONSTRUCTION | 57.53 | 35.97 | 62.52 | 55
6 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including providing FHTC and Rising main for SIDHABARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000005/2022-2023 | 15/ALD | 01/04/2022 | 30/07/2022 | BILTU DAS | 181.3 | 116.95 | 64.5 | 56
7 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 12/06/2022 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58
8 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 08/10/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 60 | 5 | 0
9 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Preparation of detailed D.P.R. booklets in connection to Sidhabari PWSS under Alipurduar-I Block under Alipurduar Division P.H.E Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000418/2022-2023 | 2821/ALD | 11/01/2023 | 10/02/2023 | ANIK BHATTACHARJEE | 0.97 | 0.97 | 100 | 56
10 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 827/ALD | 28/06/2022 | 28/06/2022 | Resource Division | 25.2 | 0 | 0 | 0
11 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Laying of HDPE and distribution pipes in different suitable locations of Sidhabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000453/2022-2023 | 2970/ALD | 31/01/2023 | 01/05/2023 | BILTU DAS | 165.16 | 58.58 | 35.47 | 61
12 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SIDHABARI water supply scheme, TW no II in the district of Alipurduar under Northern Mechanical Division-II, | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000827/2022-2023 | 489/NMD-II | 02/03/2023 | 01/04/2023 | MITRA ENTERPRISE | 9.85 | 9.7 | 98.56 | 85
13 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | SIDHABARI PIED WATER SUPPLY SCHEME | SM/10175 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sidhabari water supply scheme, TW no I in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000867/2022-2023 | 674/NMD-II | 27/03/2023 | 02/05/2025 | SOUMEN ELECTRIC | 9.87 | 7.36 | 74.61 | 100
Total | [13 empty] | 1657.87 | 289.53 | 17.46