## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Supply of CIPE Special & CI Jeffy Coupling for Mechpara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000116/2022-2023 | 708/ALD | 08/06/2022 | 08/07/2022 | TAPASH KUMAR BHOWMICK | 4.89 | 4.89 | 100 | 40
2 | ALIPURDUAR | Kalchini | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-A) | HQ-A.E | RWS Kalchini Block | ORD/000583/2021-2022 | 1967/ALD | 24/12/2021 | 24/03/2022 | HARIDAS GHOSH | 0.96 | 0.96 | 100 | 39
3 | ALIPURDUAR | Kalchini | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-A) | HQ-A.E | RWS Kalchini Block | ORD/000589/2021-2022 | 359/ALD | 08/06/2021 | 06/09/2021 | HARIDAS GHOSH | 0.96 | 0.96 | 100 | 40
4 | ALIPURDUAR | Kalchini | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 12/06/2022 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58.14
5 | ALIPURDUAR | Kalchini | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 08/10/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Construction of OHR 200cum for Mechpara Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000421/2021-2022 | 2600/ALD | 17/02/2022 | 16/08/2022 | M/S KAMAK ENGINEERS AND CO | 55.33 | 21.1 | 38.13 | 40
7 | ALIPURDUAR | Kalchini | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Supply ,delivery and installation of split type air condition for the Chamber of Division Account Office under Alipurduar Division , P.H.E Dte. | HQ-A.E |  | ORD/000499/2022-2023 | 3363/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.64 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Supply ,delivery and installation of split type air condition for the Accounts section under Alipurduar Division , P.H.E Dte. | HQ-A.E |  | ORD/000500/2022-2023 | 3364/ALD | 14/03/2023 | 13/04/2023 | HARI CONSTRUCTION | 0.64 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Mechpara TG water supply scheme, TW no I and II of under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000808/2023-2024 | 2385/NMD-II | 09/08/2023 | 08/09/2023 | B.B CONCERNED | 21.97 | 9.22 | 41.97 | 50
10 | ALIPURDUAR | Kalchini | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 826/ALD | 28/06/2022 |  | Resource Division | 30.31 | 0 | 0 | 0
11 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | New Service Connection for Mechpara T.G Area P/HNo-II, Kalchini. |  |  | BILL/02305/2023-2024 | BP-2023-24-508 | 05/01/2024 |  | WBSEDCL | 6.53 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | New Service Connection for Mechpara T.G Area P/HNo-II, Kalchini. |  |  | BILL/02305/2023-2024 | BP-2023-24-508 | 05/01/2024 |  | WBSEDCL | 6.53 | 0 | 0 | 0
13 | ALIPURDUAR | Kalchini | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 08.08.2022 to 31.10.2022) | HQ-A.E |  | ORD/000343/2022-2023 | 1191/ALD | 05/08/2022 | 03/11/2022 | NIRANJAN KIRTANIA | 0.7 | 0.2 | 28.03 | 100
14 | ALIPURDUAR | Kalchini | Alipurduar Division | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including laying distribution system, Rising main and providing FHTC for MECHPARA TEA GARDEN AREA PWSS under Alipurduar Division PHE DTE | HQ-A.E | Alipurduar Sub Division,RWS Kalchini Block | ORD/000004/2022-2023 | 14/ALD | 01/04/2022 | 30/07/2022 | SHREE RANISATI ENTERPRISE | 224.94 | 7.74 | 3.44 | 38
15 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | New Service Connection for Mechpara TG Area PWSS P/H No-I,Kalchini |  |  | BILL/02306/2023-2024 | BP-2023-24-510 | 05/01/2024 |  | WBSEDCL | 5.93 | 0 | 0 | 0
16 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | MECHPARA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10176 | New | New Service Connection for Mechpara TG Area PWSS P/H No-I,Kalchini |  |  | BILL/02306/2023-2024 | BP-2023-24-510 | 05/01/2024 |  | WBSEDCL | 5.93 | 0 | 0 | 0
Total | [13 empty] | 1567.25 | 45.06 | 2.88