## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 | New | Quotation for new service connection at Chuniya Jhora W/SS TW No- I |  |  | VCH/001327/2022-2023 | BP-14/22-23 | 14/10/2022 |  | WBSEDCL | 1.23 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 | New | Quotation for new service connection at Chuniya Jhora W/SS TW No- II |  |  | VCH/001328/2022-2023 | BP-73/22-23 | 14/10/2022 |  | WBSEDCL | 1.23 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 | New | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 12/06/2022 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 0 | 58.14
4 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 | New | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 08/10/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 100 | 8.33 | 0
5 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 | New | Construction of OHR 200cum for Chuniajhora TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000419/2021-2022 | 2598/ALD | 17/02/2022 | 16/08/2022 | AKANSHA COMMERCIAL PRIVATE LTD. | 55.36 | 47.96 | 86.64 | 65
6 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHUNIAJHORA TG AREA PWSS, TW no I (H/W Site)in the district of ALIPURDUAR under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000737/2022-2023 | 95/NMD-II | 10/01/2023 | 09/02/2023 | DIAMOND ELECTRICAL WORKS | 9.83 | 9.79 | 99.66 | 65
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHUNIAJHORA TG AREA PWSS, TW no II in the district of ALIPURDUAR under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000736/2022-2023 | 94/NMD-II | 10/01/2023 | 09/02/2023 | BONANZA ENTERPRISE | 9.84 | 9.78 | 99.42 | 65
8 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including laying distribution system, Rising main and providing FHTC for CHUNIAJHORA TEA GARDEN AREA PWSS under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000002/2022-2023 | 12/ALD | 01/04/2022 | 30/07/2022 | AKANSHA COMMERCIAL PRIVATE LTD. | 168.43 | 143.64 | 85.28 | 100
9 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 | New | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 397/ALD | 11/05/2022 |  | Resource Division | 3.59 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUNIA JHORA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/10179 | New | Laying of HDPE/DI Pipeline, horizontal boring by HDD method, bridge and culvert crossing, providing FHTC, specials repair with trial run of pipeline and allied works at Chuniajhora PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000460/2023-2024 | 672/ALD | 06/03/2024 | 04/06/2024 | ASHOK SAPKOTA | 19.39 | 0 | 0 | 5
Total | [13 empty] | 1469.88 | 311.17 | 21.17