## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Installation of 125mm X 80mm X 90 mtr. Deep Tube Well (Mark-II TW) for fresh drinking water sources(with provision of lowering of sub-merssible pump) by ODEX-115 method of Drilling Near House of Lt. Jhagru Rai, East Hirdaypur of Angrabhasa GP-I under Nagrakata Block under Jalpaiguri District. | HQ-A.E |  | ORD/000406/2020-2021 | 1827/ALD | 23/02/2021 | 10/03/2021 | RAMESH SHARMA | 4.08 | 0 | 0 | 40
2 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Construction of RCC boundary wall for Uttar Latabari WSS Pump House (rabindra nagar) at Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000268/2021-2022 | 1834/ALD | 10/12/2021 | 24/01/2022 | SHIB RATAN BHOWMIK | 4.9 | 4.48 | 91.34 | 75
3 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Providing Functional Tap Connection from existing pipeline to the schools, AWC, Community centres, Govt. Office Buildings and Households at Southern Part of Uttar Latabari Area under Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000249/2021-2022 | 1594/ALD | 22/11/2021 | 22/12/2021 | M/S SHIB RATAN BHOWMICK & CO | 4.99 | 4.99 | 100 | 76
4 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Providing Functional Tap Connection from existing pipeline to the schools, AWC, Community centres, Govt. Office Buildings and Households at Northern Part of Uttar Latabari Area under Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000250/2021-2022 | 1595/ALD | 22/11/2021 | 22/12/2021 | M/S SHIB RATAN BHOWMICK & CO | 4.99 | 4.99 | 100 | 75
5 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Retrofitting of pipeline for UTTAR LATABARAI PWSS (Rabindranagar & surroundings) area at Kalchini Block under Alipurduar Division, PHE Dte. Part-A | HQ-A.E | RWS Kalchini Block | ORD/000273/2020-2021 | 1285/ALD | 05/01/2021 | 06/03/2021 | ASHOK SAPKOTA | 22.45 | 3.32 | 14.78 | 46
6 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Retrofitting of pipeline for UTTAR LATABARAI PWSS (Rabindranagar & surroundings) area at Kalchini Block under Alipurduar Division, PHE Dte. Part-B | HQ-A.E | Birpara Sub Division | ORD/000274/2020-2021 | 1286/ALD | 05/01/2021 | 06/03/2021 | ASHOK SAPKOTA | 19.09 | 6.87 | 35.99 | 45
7 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Uttar Latabari PWSS under Alipurduar Division, PHE Dte. Part-3 | HQ-A.E | Birpara Sub Division | ORD/000103/2022-2023 | 407/ALD | 11/05/2022 | 25/06/2022 | SHIB RATAN BHOWMIK | 24.21 | 8.68 | 35.86 | 46
8 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Laying of DI and HDPE pipeline from Kalchini BDO Office towards Hamiltonganj Bazar at Uttar Latabari PWSS area under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000294/2022-2023 | 1685/ALD | 20/09/2022 | 19/11/2022 | SUNDAR SING LAMA | 24.01 | 23.09 | 96.16 | 45
9 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Uttar Latabari PWSS under Alipurduar Division, PHE Dte. Part-2 | HQ-A.E | Birpara Sub Division | ORD/000102/2022-2023 | 406/ALD | 11/05/2022 | 25/06/2022 | ASHOK SAPKOTA | 24.2 | 20.74 | 85.71 | 42
10 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Laying of HDPE pipeline for providing FHTC at Uttar Latabari PWSS area, Kalchini Block under Alipurduar Division PHE DTE. | HQ-A.E | Birpara Sub Division | ORD/000238/2022-2023 | 1330/ALD | 24/08/2022 | 23/10/2022 | DIPANKAR DUTTA | 47.46 | 47.24 | 99.53 | 46
11 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Providing balance FHTC from existing distribution system as per specification for UTTAR LATABARI PWSS under Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000295/2023-2024 | 2104/ALD | 29/09/2023 | 28/12/2023 | DIPANKAR DUTTA | 65.07 | 0 | 0 | 0
12 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Reparing of Pump House at Headwork site of Uttar Latabari PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000595/2024-2025 | 5424/ALD | 19/03/2025 | 18/05/2025 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0 | 0
13 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Reparing of Pump House at 2nd site of Uttar Latabari PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000597/2024-2025 | 5426/ALD | 19/03/2025 | 18/05/2025 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0 | 0
14 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | Reparing of Pump House at 4th site of Uttar Latabari PWSS Under Alipurduar Division PHE DTE |  |  | ORD/000596/2024-2025 | 5425/ALD | 19/03/2025 | 18/05/2025 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0 | 0
15 | ALIPURDUAR |  | Alipurduar Division | Providing FHTC of existing LDS under command area UTTARLATABARI WSS at Kalchini Block. | SM/10637 | Augmentation | HDPE pipeline for leftout household connection and gap joint works under Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block,RWS Kumargram Block | ORD/000455/2024-2025 | 5172/ALD | 25/02/2025 | 31/07/2025 | PRAPTI DUTTA | 9.61 | 0 | 0 | 100
Total | [13 empty] | 257.87 | 124.4 | 48.24