## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Retrofitting of pipeline etc. for "Jal Swapno Program" (FHTC for every house hold) under Purba Chenpani PWSS under Alipurduar-II Block under Alipurduar Division, PHE Dte.(Re-tenter) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000079/2022-2023 | 443/ALD | 13/05/2022 | 12/06/2022 | MATRI ENTERPRISE | 4.2 | 4.06 | 96.71 | 10
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Construction of pump House, boundary wall, laying of UPVC pipe linr & Rising main connection for Purba Chepani PWSS proposed 4th TW SITE under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000519/2022-2023 | 3494/ALD | 23/03/2023 | 21/06/2023 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 41.66 | 0 | 0 | 48
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Providing balance FHTC for Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000247/2023-2024 | 1589/ALD | 25/08/2023 | 24/09/2023 | ANIRBAN KAR | 3.32 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000193/2022-2023 | 1220/ALD | 10/08/2022 | 09/10/2022 | SREE MAA CONSTRUCTION | 21.55 | 9.35 | 43.4 | 94
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 3607/ALD | 24/10/2024 | 24/10/2024 | Resource Division | 5.11 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Sinking of 250 mm x 200 mm x 150 mtr Big dia TW by reverse rotary drilling method at 4th TW site of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000028/2025-2026 | 437/ALD | 30/04/2025 | 30/05/2025 | MADHAB SAHA | 11.51 | 0 | 0 | 0
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Laying of UPVC Pipeline Distrbutation system, Delivery line connection, Cons. of surface drain, Pathway and Land Development works for 4th site at Paschim Chepani under Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000072/2025-2026 | 970/ALD | 12/06/2025 | 10/09/2025 | PROGRESSIVE UN EMPLOYED CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD | 38.43 | 0 | 0 | 0
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA CHEPANI WATER SUPPLY SCHEME | SM/10669 | Augmentation | Restoration of damaged FHTCs of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000074/2025-2026 | 972/ALD | 12/06/2025 | 27/07/2025 | KOUSHIK BHOWMICK | 2.44 | 0 | 0 | 0
Total | [13 empty] | 266.58 | 13.42 | 5.03