## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | SM/10678 | Augmentation | NEW SERVICE CONNECTION AT JOGENDRAPUR TW III |  |  | BILL/01972/2023-2024 | BP-2023-24-462 | 07/12/2023 | 07/12/2023 | WBSEDCL | 5.36 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | SM/10678 | Augmentation | Laying distribution line, providing road and culvert crossing, and providing FHTC for Jogendrapur and Satpukuria Mouzas and adjacent areas, Cons. of Tubewell by ODEX-165 method of drilling, cons. of pump house and boundary wall for augmentation of JOGENDRAPUR PWSS. (2nd call) | Birpara A.E | Birpara Sub Division | ORD/000481/2022-2023 | 3198/ALD | 27/02/2023 | 26/08/2023 | BIJOY ROY | 159.61 | 67.65 | 42.39 | 25
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | SM/10678 | Augmentation | Laying of different dia DI,UPVC pipeline, bridge and culvert crossing and other works for providing FHTC at Jogendrapur and Satpukuri mouza at Augmentation of Jogendrapur PWSS under Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/10678) | Birpara A.E | Birpara Sub Division | ORD/000230/2024-2025 | 2283/ALD | 05/08/2024 | 04/10/2024 | MONORAMA ENTERPRISE | 21.88 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | SM/10678 | Augmentation | Supply of fuel for Diesel Vehicle Maxi Cab(At least 7 seater ) (Preferably TUV) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte.(from 08/08/2022 to 31.12.2022) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000178/2022-2023 | 1184/ALD | 05/08/2022 | 05/01/2023 | MATRI ENTERPRISE | 1.27 | 0 | 0 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | SM/10678 | Augmentation | Painting of Old OHR at Jogendrapur PWSS (400cum) under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000440/2024-2025 | 5044/ALD | 17/02/2025 | 03/04/2025 | DILIP MAHATO (OPC) PRIVATE LIMITED | 3.14 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF JOGENDRAPUR WATER SUPPLY SCHEME | SM/10678 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Birpara A.E | RWS Falakata Block | ORD/000130/2025-2026 | 1629/ALD | 04/08/2025 | 03/10/2025 | NARENDRA BHADANI. | 18.13 | 0 | 0 | 0
Total | [13 empty] | 209.38 | 67.65 | 32.31