## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata,Kumargram,Madarihat | Alipurduar Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER ALIPURDUAR DISTRICT PIPED WATER SUPPLY SCHEME | SM/10776 | New | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 967/ALD | 15/07/2022 | 15/07/2022 | Resource Division | 1.43 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata,Kumargram,Madarihat | Alipurduar Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER ALIPURDUAR DISTRICT PIPED WATER SUPPLY SCHEME | SM/10776 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME IN 4(Four) nos. villages under different blocks having less than 100 household under Alipurduar district in connection with Jal Swapna. | Alipurduar RWS,Birpara A.E | JUNIOR ENGINEER,RWS Falakata Block,RWS Madarihat - Birpara Block | ORD/000101/2022-2023 | 605/ALD | 31/05/2022 | 01/01/2025 | M/S KAMAK ENGINEERS AND CO | 159.94 | 0 | 0 | 90
Total | [13 empty] | 161.36 | 0 | 0