## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying Distribution of pipeline with DI and UPVC pipeline along with FHTC Connection for Purba Kathalbari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000158/2022-2023 | 988/ALD | 15/07/2022 | 13/09/2022 | NEOGI ENTERPRISE | 98.79 | 80.1 | 81.08 | 30
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Purba Kathalbari Zone-IV PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000143/2022-2023 | 980/ALD | 15/07/2022 | 11/01/2023 | MAHENDRA CHHETRI | 46.09 | 27.06 | 58.71 | 60
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of 150cum. OHR for PURBA KATHALBARI ZONE-IV Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000149/2022-2023 | 984/ALD | 15/07/2022 | 04/07/2024 | MAHENDRA CHHETRI | 50.44 | 29.62 | 58.73 | 52
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Purba Kathalbari Zone-III PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000168/2022-2023 | 1008/ALD | 15/07/2022 | 13/10/2022 | MADHAB SAHA | 45.9 | 39.6 | 86.27 | 86
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of OHR 200cum for PURBA KATHALBARI ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000161/2022-2023 | 991/ALD | 15/07/2022 | 11/01/2023 | MS DEYS CONSTRUCTION | 55.5 | 25 | 45.05 | 55
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Southern side of Purba Kathalbari Zone (II) PWSS and surrounding areas at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000167/2022-2023 | 997/ALD | 15/07/2022 | 13/09/2022 | M/S JHA CONSTRUCTION | 99.69 | 76.99 | 77.23 | 27
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Northern side of Purba Kathalbari Zone (II) PWSS and surrounding areas at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000141/2022-2023 | 978/ALD | 15/07/2022 | 13/09/2022 | DILIP MAHATO | 99.77 | 76.96 | 77.14 | 15
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Purba Kathalbari Zone-II PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000142/2022-2023 | 979/ALD | 15/07/2022 | 04/07/2024 | JYOTI CHHETRI | 45.88 | 19.14 | 41.71 | 20
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection surrounding Sirubari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000163/2022-2023 | 993/ALD | 15/07/2022 | 05/09/2024 | MS DEYS CONSTRUCTION | 99.93 | 58.95 | 58.99 | 85
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Purba Kathalbari Zone(IV) PWSS area and surrounding, Alipurduar-I Block under Alipurduar Division, PHE Dte.(Part-A) | Alipurduar RWS | Birpara Sub Division | ORD/000165/2022-2023 | 995/ALD | 15/07/2022 | 13/09/2022 | DAS ENTERPRISE | 99.06 | 67.23 | 67.87 | 27
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Purba Kathalbari PWSS under Alipurduar Division, PHE Dte. Part-3 | Alipurduar RWS | Birpara Sub Division | ORD/000144/2022-2023 | 981/ALD | 15/07/2022 | 29/08/2022 | MAHENDRA CHHETRI | 24.2 | 7.33 | 30.29 | 26
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for PurbaKathalbari PWSS under Alipurduar Division, PHE Dte. Part-4 | Alipurduar RWS | Birpara Sub Division | ORD/000145/2022-2023 | 982/ALD | 15/07/2022 | 29/08/2022 | DAS CONSTRUCTION | 24.14 | 0 | 0 | 27
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying Distribution of pipeline with DI and UPVC pipeline along with FHTC Connection at Jogendranagar area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000159/2022-2023 | 989/ALD | 15/07/2022 | 13/09/2022 | UTTAM KUMAR DUTTA | 98.45 | 87.43 | 88.8 | 27
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection surrounding Palashbari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000164/2022-2023 | 994/ALD | 15/07/2022 | 11/01/2023 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 87.56 | 44.57 | 50.91 | 28
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of different dia. Pipeline and providing FHTC for Purba Kathalbari Zone(IV) PWSS area and surrounding area of NH-31D at Alipurduar-I Block under Alipurduar Division, PHE Dte.(Part-B) | Alipurduar RWS | Birpara Sub Division | ORD/000166/2022-2023 | 996/ALD | 15/07/2022 | 13/09/2022 | NARAYAN CHANDRA SAHA | 99.18 | 75.08 | 75.7 | 76
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Development of TW, Yield testing with BHT Pump and water sample collection and chemical test at different tubewell of Purba Kathal Bari PWSS at Alipurduar-I Block, Alipurduar Division PHED. | Alipurduar RWS |  | ORD/000351/2022-2023 | 2495/ALD | 13/12/2022 | 11/02/2023 | SAMIRON PODDER | 5.68 | 0 | 0 | 0
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000416/2022-2023 | 2731/ALD | 30/12/2022 | 30/12/2023 | KAMALESH ROY | 4.8 | 0 | 0 | 100
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Deputy Superintending Engineer, North Bengal Circle-I , P.H.E. Dte.(from 01.03.2023 to 29.02.2024) | HQ-A.E | Birpara Sub Division | ORD/000473/2022-2023 | 3232/ALD | 27/02/2023 | 27/02/2024 | MAHENDRA CHHETRI | 4.8 | 0 | 0 | 0
19 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-I under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000801/2022-2023 | 368/NMD-II | 22/02/2023 | 24/03/2023 | ALPHA ENTERPRISE | 22.84 | 9.79 | 42.87 | 60
20 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-IV under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000050/2023-2024 | 1107/NMD-II | 05/06/2023 | 05/07/2023 | SUMON ELECTRICAL | 22.86 | 10.1 | 44.2 | 70
21 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-II under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000794/2023-2024 | 2366/NMD-II | 08/08/2023 | 07/09/2023 | SUMON ELECTRICAL | 22.5 | 0 | 0 | 0
22 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Providing FHTC from existing distribution system as per specification for PURBA KATHALBARI PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000288/2023-2024 | 1996/ALD | 15/09/2023 | 14/11/2023 | M/S SIBU DEY AND CO | 24.2 | 0 | 0 | 0
23 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of 250cum OHR for PURBA KATHALBARI ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar RWS | ORD/000155/2022-2023 | 987/ALD | 15/07/2022 | 11/01/2023 | NEOGI ENTERPRISE | 57.61 | 19.01 | 33 | 35
24 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site along with repairing of 1 no. pump house for Purba Kathalbari Zone-I PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000169/2022-2023 | 1007/ALD | 15/07/2022 | 13/10/2022 | SAMIRON PODDER | 43.06 | 40.49 | 94.02 | 0
25 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Construction of OHR 200cum for PURBA KATHALBARI ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000152/2022-2023 | 986/ALD | 15/07/2022 | 11/01/2023 | MADHAB SAHA | 55.36 | 34.75 | 62.77 | 51
26 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2024 to 31.12.2024) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000499/2023-2024 | 488/ALD | 15/02/2024 | 14/02/2025 | SASANKA ROY | 4.8 | 0 | 0 | 0
27 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of DI and HDPE pipeline, Trenchless Pipe laying by HDD Process & other works for PURBA KATHALBARI ZONE-I 3rd pump house area for Purba Kathalbari PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/11459) | Alipurduar RWS | Birpara Sub Division | ORD/000503/2023-2024 | 821/ALD | 14/03/2024 | 12/07/2024 | KAJAL KUMAR DE | 39.26 | 0 | 0 | 0
28 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of different dia., CIDF, DI, UPVC, HDPE Pipeline, Trenchless Pipe laying by HDD Process, HDPE pipe line for left out household connection, Trial and run the entire PURBA KATHALBARI ZONE-4 PWSS Scheme with maintaining for 3 months after successfully running water, cons. of surface drain, pathway at H/W site and other works for Purba Kathalbari PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/11459) | Alipurduar RWS | Birpara Sub Division | ORD/000530/2023-2024 | 849/ALD | 14/03/2024 | 12/07/2024 | NARENDRA BHADANI. | 57.56 | 9.4 | 16.33 | 12
29 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Laying of different dia., CIDF, DI, UPVC, HDPE Pipeline, Trenchless Pipe laying by HDD Process, HDPE pipe line for left out household connection,Trial and run the entire PURBA KATHALBARI ZONE-3 PWSS Scheme with maintaining for 3 months after successfully running water, cons. of surface drain, pathway at H/W site and other works works for Purba Kathalbari PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/11459) | Alipurduar RWS |  | ORD/000534/2023-2024 | 892/ALD | 15/03/2024 | 13/07/2024 | MADHAB SAHA | 49.29 | 0 | 0 | 0
30 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Schedule for: Supply, delivery and installation of 30 KVA servo motor operated Copper wound line voltage corrector at Purba Kathalbari Water Supply Scheme TW No.-II under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000651/2021-2022 | 1097/NMD-II | 20/09/2021 | 20/10/2021 | NIRMAN | 3.94 | 3.94 | 100 | 0
31 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Soil investigation work at 4 different places of Purba Kanthalbari within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar RWS |  | ORD/000157/2022-2023 | 1006/ALD | 15/07/2022 | 14/08/2022 | MABCO CONSULTANT, | 4.87 | 4.87 | 100 | 27
32 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Purba Kanthalbari water supply scheme, TW no I and II of Zone-III under Northern Mechanical Division-II, PHE Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000048/2023-2024 | 1085/NMD-II | 01/06/2023 | 01/07/2023 | M/S P.P ELECTRICALS | 22.85 | 10.73 | 46.95 | 100
33 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 1590/ALD | 14/09/2022 |  | Resource Division | 130.15 | 0 | 0 | 0
34 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 3612/ALD | 24/10/2024 |  | Resource Division | 7.78 | 0 | 0 | 0
35 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-IV P/H NO.I |  |  | BILL/00676/2023-2024 | BP-2023-24-198 | 22/06/2023 |  | WBSEDCL | 1.71 | 0 | 0 | 0
36 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-III P/H NO.II |  |  | BILL/00678/2023-2024 | BP-2023-24-196 | 22/06/2023 |  | WBSEDCL | 1.71 | 0 | 0 | 0
37 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-I P/H NO.II |  |  | BILL/00679/2023-2024 | BP-2023-24-195 | 22/06/2023 |  | WBSEDCL | 1.71 | 0 | 0 | 0
38 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR PURBA KATHALBARI zONE-III P/H NO.I |  |  | BILL/00677/2023-2024 | BP-2023-24-197 | 22/06/2023 |  | WBSEDCL | 1.71 | 0 | 0 | 0
39 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT PURBA KATHALBARI PWSS PALASHBARI, FLOOD SHELTER, ZONE-I,P/H NO-I |  |  | BILL/01448/2023-2024 | BP-2023-24-293 | 21/08/2023 |  | WBSEDCL | 6.38 | 0 | 0 | 0
40 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR PURBA KATHALBARI PWSS ZONE-II P/H NO-II |  |  | BILL/02806/2023-2024 | BP-2023-24-646 | 29/02/2024 |  | WBSEDCL | 9.8 | 0 | 0 | null
41 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | QUOTATION CHARGES FOR PURBAKATHALBARI PWSS, ZONE-II PH NO-II |  |  | BILL/00276/2024-2025 | BP-80/24-25 | 16/05/2024 |  | WBSEDCL | 11.03 | 0 | 0 | null
42 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF PURBA KATHALBARI WATER SUPPLY SCHEME | SM/11459 | Augmentation | New Service Connection charges for Purba Kathalbari Zone-IV PH NO-II under NMD-II |  |  | BILL/01888/2024-2025 | null | 05/12/2024 |  | WBSEDCL | 6.36 | 0 | 0 | null
Total | [13 empty] | 1699.19 | 858.12 | 50.5