## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Construction of Pump House,Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for NEWLANDS TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000213/2022-2023 | 1307/ALD | 22/08/2022 | 20/12/2022 | MADHAB SAHA | 97.2 | 91.59 | 94.23 | 94
2 | ALIPURDUAR | Kumargram | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Providing balance FHTC for NEWLAND TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000246/2023-2024 | 1792/ALD | 29/08/2023 | 28/10/2023 | SUBHAK CHIK BARAIK | 13.39 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 188/ALD | 28/04/2023 | 28/04/2023 | Resource Division | 18.72 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Quotation for new service connection at Newland TG P/H No-II. Application No- 4003039064 |  |  | BILL/00021/2022-2023 | BP-104/22-23 | 19/12/2022 | 19/12/2022 | WBSEDCL | 1.58 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Quotation for new service connection at Newland TG P/H No-I. Application No- 4003039040 |  |  | BILL/00020/2022-2023 | BP-103/22-23 | 19/12/2022 | 19/12/2022 | WBSEDCL | 1.58 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.08.2022 to 31.10.2022) | HQ-A.E |  | ORD/000201/2022-2023 | 1122/ALD | 29/07/2022 | 29/10/2022 | NIRANJAN KIRTANIA | 0.5 | 0.5 | 100 | 100
7 | ALIPURDUAR | Kumargram | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2022 to 31.01.2023) | HQ-A.E |  | ORD/000344/2022-2023 | 2013/ALD | 28/10/2022 | 28/01/2023 | NIRANJAN KIRTANIA | 0.7 | 0.47 | 67.38 | 100
8 | ALIPURDUAR | Kumargram | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2022 to 31.01.2023) | HQ-A.E |  | ORD/000345/2022-2023 | 2014/ALD | 28/10/2022 | 28/01/2023 | NIRANJAN KIRTANIA | 0.5 | 0.5 | 100 | 100
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for New Land TG water supply scheme, TW no II in the district of Alipurduar under Northern Mechanical Division-II PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000865/2022-2023 | 664/NMD-II | 24/03/2023 | 23/04/2023 | SARKAR ELECTRIC | 10.46 | 10.39 | 99.38 | 90
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for New Land TG water supply scheme, TW no I in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000072/2023-2024 | 1254/NMD-II | 04/07/2023 | 03/08/2023 | MALAY KUMAR SAHA | 10.44 | 10.32 | 98.82 | 90
11 | ALIPURDUAR | Kumargram | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Material Requisition To Resource Division |  |  | RTOR000043/2024-2025 | 4259/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 11.34 | 0 | 0 | 0
12 | ALIPURDUAR | Kumargram | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
13 | ALIPURDUAR | Kumargram | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Construction of Pump House,Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for NEWLANDS TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000206/2022-2023 | 1275/ALD | 17/08/2022 | 31/12/2023 | TAPASH KUMAR BHOWMICK | 96.78 | 90.66 | 93.68 | 95
14 | ALIPURDUAR | Kumargram | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Laying of Rising Main line with HDPE PN 10, bridge and culvert crossing, cons. Of pathway, surface drain and chatal, Installation of Paver block, land development along with the other allied works at Newlands TG H/W Site under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000336/2023-2024 | 391/ALD | 05/02/2024 | 30/04/2025 | K S ENTERPRISE | 48.23 | 0 | 0 | 65
15 | ALIPURDUAR | Kumargram | Alipurduar Division | NEWLANDS TG AREA PIPED WATER SUPPLY SCHEME | SM/11484 | New | Construction of 250cum. OHR for Newlands TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000138/2022-2023 | 975/ALD | 15/07/2022 | 31/08/2025 | TAPASH KUMAR BHOWMICK | 57.61 | 41.99 | 72.89 | 75
Total | [13 empty] | 433.04 | 246.43 | 56.91