## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Construction of 250cum. OHR for Sankosh TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000140/2022-2023 | 977/ALD | 15/07/2022 | 11/01/2023 | SOUVIK ROY PALADHI | 57.62 | 39.52 | 68.59 | 80
2 | ALIPURDUAR | Kumargram | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Construction of Pump House,Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for SANKOSH TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000207/2022-2023 | 1276/ALD | 17/08/2022 | 15/12/2022 | SOUVIK ROY PALADHI | 96.66 | 90.94 | 94.08 | 50
3 | ALIPURDUAR | Kumargram | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for SANKOSH TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000208/2022-2023 | 1277/ALD | 17/08/2022 | 15/12/2022 | SOUVIK ROY PALADHI | 83.75 | 73.88 | 88.21 | 70
4 | ALIPURDUAR | Kumargram | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 1591/ALD | 14/09/2022 | 14/09/2022 | Resource Division | 6.68 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Quotation for new service connection at Sankosh TG P/H No-I. Application No- 4003039354 |  |  | BILL/00022/2022-2023 | BP-105/22-23 | 19/12/2022 | 19/12/2022 | WBSEDCL | 1.58 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Quotation for new service connection at Sankosh TG P/H No-II. Application No- 4003039376 |  |  | BILL/00023/2022-2023 | BP-106/22-23 | 19/12/2022 | 19/12/2022 | WBSEDCL | 1.58 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Providing balance FHTC for SANKOSH TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000244/2023-2024 | 1790/ALD | 29/08/2023 | 12/02/2025 | SOUVIK ROY PALADHI | 12.27 | 0 | 0 | 75
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sankosh water supply scheme, TW no I(H/W Site) under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000010/2023-2024 | 860/NMD-II | 26/04/2023 | 26/05/2023 | SAIKAT SINHA | 10.76 | 10.66 | 99.09 | 100
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sankosh water supply scheme, TW no II under Northern Mechanical Division-II, PHEDte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000011/2023-2024 | 864/NMD-II | 26/04/2023 | 26/05/2023 | KARMAKAR CONSTRUCTION | 10.74 | 10.62 | 98.9 | 90
10 | ALIPURDUAR | Kumargram | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Supply of CIDF & CISS Pipes and specials for Sankos TG WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000236/2023-2024 | 1592/ALD | 25/08/2023 | 16/02/2025 | SOUVIK ROY PALADHI | 6.76 | 5.24 | 77.53 | 100
11 | ALIPURDUAR | Kumargram | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 189/ALD | 28/04/2023 | 28/04/2023 | Resource Division | 15.48 | 0 | 0 | 0
12 | ALIPURDUAR | Kumargram | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Laying of Rising Main line with HDPE PN 10, bridge and culvert crossing, cons. Of pathway, surface drain and chatal, Installation of Paver block, land development along with the other allied works at Sankosh TG H/W Site under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000335/2023-2024 | 390/ALD | 05/02/2024 | 30/04/2025 | K S ENTERPRISE | 48.17 | 0 | 0 | 65
13 | ALIPURDUAR | Kumargram | Alipurduar Division | SANKOSH TG AREA PIPED WATER SUPPLY SCHEME | SM/11485 | New | Laying of HDPE/DI Pipeline for filling up the gap & bridge / culvert crossing, specials repair with trial run of pipeline and allied works at Sankosh TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000398/2023-2024 | 209/ALD | 16/01/2024 | 10/04/2025 | SOUVIK ROY PALADHI | 19.84 | 3.66 | 18.43 | 80
Total | [13 empty] | 371.88 | 234.52 | 63.06