## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 | New | Soil investigation works at head works site for HOASINBAD TG AREA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000309/2022-2023 | 2133/ALD | 10/11/2022 | 10/12/2022 | MOYTEC | 0.7 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 | New | QUOTATION FOR NEW SERVICE CONNECTION AT HOASINABAD TG TW NO-I |  |  | BILL/00063/2023-2024 | BP-2023-24-56 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.6 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 | New | QUOTATION FOR NEW SERVICE CONNECTION AT HOASINABAD TG TW NO-II |  |  | BILL/00062/2023-2024 | BP-2023-24-57 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.6 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 | New | Laying of DI and HDPE pipeline, trenchless pipe laying by HDD process, providing FHTC and others for Hossainabad PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000472/2023-2024 | 690/ALD | 07/03/2024 | 02/12/2024 | SASANKA ROY | 62.82 | 0 | 0 | 80
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Hosainbad TG water supply scheme, TW no. I and II under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000826/2022-2023 | 485/NMD-II | 02/03/2023 | 01/04/2023 | MITRA ENTERPRISE | 27.77 | 0 | 0 | 99
6 | ALIPURDUAR | Madarihat | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 | New | Construction of 2nos. Pump house, 2nos. Boundary wall at headwork site and 2nd Tubewell site including providing FHTC for HOASINBAD TG AREA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000282/2022-2023 | 1636/ALD | 19/09/2022 | 30/04/2025 | RATAN DUTTA | 37.7 | 0 | 0 | 80
7 | ALIPURDUAR | Madarihat | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 | New | Laying of distribution system (Part-2) and providing FHTC for HOASINBAD TG AREA PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000283/2022-2023 | 1637/ALD | 19/09/2022 | 30/08/2023 | SASANKA ROY | 81.64 | 0 | 0 | 92
8 | ALIPURDUAR | Madarihat | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 | New | Construction of 200 cum OHR as per Departmental Design and drawing in headwork site, Tube well Boring by ODEX-165 method of drilling 2nos. respectively at Headwork site and 2nd Tubewell site, Rising Main and distribution line (Part-1) for HOASINBAD TG AREA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte | Birpara A.E | Alipurduar Sub Division | ORD/000281/2022-2023 | 1635/ALD | 19/09/2022 | 05/04/2025 | SASANKA ROY | 96.32 | 0 | 0 | 95
9 | ALIPURDUAR | Madarihat | Alipurduar Division | HOASINBAD TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11696 | New | Laying of additional HDPE pipeline for Gap filling and providing FHTC at Hoasinbad TG under Hoasinbad PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000068/2025-2026 | 966/ALD | 12/06/2025 | 11/08/2025 | SASANKA ROY | 26.04 | 0 | 0 | 0
Total | [13 empty] | 336.18 | 0 | 0