## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | DRINKINH WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KIT (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION | SM/11752 | Support-WQMSP | Uploading Charges of FTK results under Alipurduar Division PHE Dte. | Alipurduar RWS |  | ORD/000188/2023-2024 | 1206/ALD | 07/08/2023 | 05/12/2023 | TAPASH KUMAR BHOWMICK | 0.4 | 0.4 | 100 | 100
2 | ALIPURDUAR |  | Alipurduar Division | DRINKINH WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KIT (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION | SM/11752 | Support-WQMSP | Sample collection from different facilator less gram panchayat for 12 months under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division,JUNIOR ENGINEER | ORD/000344/2023-2024 | 2545/ALD | 28/11/2023 | 28/11/2024 | JAYDAB ADHIKARI | 9.81 | 8.77 | 89.37 | 100
3 | ALIPURDUAR |  | Alipurduar Division | DRINKINH WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KIT (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION | SM/11752 | Support-WQMSP | PLAN TO TEST SCHOOLS AND ANGANAWADI CENTRES WRT "SWACHH JAL SURAKSHA" CAMPAIGN |  |  | BILL/00041/2023-2024 | 141/23-24/PFMS | 22/08/2023 | 22/08/2023 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.81 | 0 | 0 | 0
4 | ALIPURDUAR |  | Alipurduar Division | DRINKINH WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KIT (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION | SM/11752 | Support-WQMSP | Uploading charges of Field Test Kit(FTK) Results under Alipurduar Division , PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000152/2025-2026 | 1589/ALD | 31/07/2025 | 27/05/2026 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.8 | 0 | 0 | 90
5 | ALIPURDUAR |  | Alipurduar Division | DRINKINH WATER SAMPLE COLLECTION & TESTING THROUGH FIELD TEST KIT (FTKs) & UPLOADING CHARGES FOR THE SAME RELATED TO WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME UNDER JAL JEEVAN MISSION | SM/11752 | Support-WQMSP | Procurement of Field Test Kits (FTK) For water quality testing using FTK/H2S vials in the district of Alipurduar related to Water Quality Monitoring & Surveillance Activities under Jal Jeevan Mission under PHE DTE. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000608/2024-2025 | 5598/ALD | 27/03/2025 | 26/05/2025 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 0.89 | 0 | 0 | 100
Total | [13 empty] | 14.71 | 9.17 | 62.32