## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME | SM/11765 | Augmentation | Supply, installation, commissioning and Trial operation of Electro Mechanical components of TOTOPARA Water Supply Scheme TW No.-IV under NMD-II,PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000756/2021-2022 | 69/NMD-II | 24/01/2022 | 23/02/2022 | SUNLIT | 7.57 | 7.57 | 100 | 0
2 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME | SM/11765 | Augmentation | Supply, delivery and installation of 15 KVA servo motor operated Copper wound line voltage corrector at TOTOPARA Water Supply Scheme TW No.-III under NMD-II, PHE.Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000762/2021-2022 | 1096/NMD-II | 20/09/2021 | 20/10/2021 | SUNLIT | 2.38 | 2.38 | 100 | 0
3 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME | SM/11765 | Augmentation | Supply, delivery & installation of 15 KVA, Servo Motor operated Copper wound line voltage stabilizer of Totopara Water Supply Scheme TW No.-IV under NMD-II, PHE. Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000881/2021-2022 | 1374/NMD-II | 22/12/2021 | 21/01/2022 | SANJIB SAHA | 2.15 | 2.15 | 100 | 0
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME | SM/11765 | Augmentation | Laying of overground distribution system by using HDPE pipes under Augmentation of Totopara PWSS under Alipurduar Division PHE Dte. | Birpara A.E | RWS Madarihat - Birpara Block | ORD/000001/2023-2024 | 04/ALD | 04/04/2023 | 03/06/2023 | DULAL DAS | 39.82 | 39.61 | 99.47 | 100
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF TOTOPARA AREA PIPED WATER SUPPLY SCHEME | SM/11765 | Augmentation | Construction of intake structure ground level reservoir, boundary wall, Pump House, laying of distribution network and providing FHTC under Augmentation of Totopara PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E,HQ-A.E | JUNIOR ENGINEER | ORD/000352/2023-2024 | 2604/ALD | 04/12/2023 | 26/07/2025 | DULAL DAS | 63.1 | 12.27 | 19.44 | 35
Total | [13 empty] | 115.02 | 63.97 | 55.62