## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Providing House connection at LANKAPARA TG (Part-A) PWSS under Alipuduar Division, P.H.E. Dte. | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000364/2020-2021 | 1807/ALD | 22/02/2021 | 31/08/2023 | GHOSH & SAHA CONSTRUCTION | 41.88 | 0 | 0 | 50
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Bridge Crossing and Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS under Alipurduar Division, PHE Dte. Dist-Alipurduar. | Birpara A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000270/2020-2021 | 1282/ALD | 05/01/2021 | 01/01/2023 | GHOSH & SAHA CONSTRUCTION | 23.75 | 7.39 | 31.14 | 100
3 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Yard lighting arrangement at Lankapara Water supply scheme ( Head Work site ) Under Northern Mechanical Division-II P.H.E Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000644/2021-2022 | 1103/NMD-II | 20/09/2021 | 20/10/2021 | SAIKAT SINHA | 3.16 | 3.16 | 100 | 12
4 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Supply, delivery & installation of 30 KVA, Servo Motor operated Copper wound line voltage stabilizer of Lankapara Water Supply scheme T/W No.VI NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000777/2021-2022 | 166/NMD-II | 22/02/2022 | 24/03/2022 | M/S A.D ENTERPRISE | 3.17 | 2.42 | 76.35 | 11
5 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Lankapara Water Supply Scheme TW No.-VI under NMD-II,PHE Dte Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000824/2021-2022 | 204/NMD-II | 24/02/2022 | 26/03/2022 | SARKAR ELECTRIC | 10.46 | 10.46 | 100 | 10
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Construction of river bank protection wall with wire create and land filling near 3 No. PHE pump house at SK Line under Lankapara GP within Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000352/2022-2023 | 2496/ALD | 13/12/2022 | 13/03/2023 | RATAN DUTTA | 1.31 | 1.17 | 89.28 | 100
7 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Supply, delivery & installation of 30 KVA, Servo Motor operated Copper wound line voltage stabilizer Lankapara Water Supply Scheme TW No.-V under NMD-II,PHE.Dte,Coochbehar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000859/2021-2022 | 185/ NMD-II | 23/02/2022 | 25/03/2022 | M/S PALI DEB ENGINEERING | 3.16 | 3.16 | 100 | 12
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Tube well Boring by ODEX-195 Method of drilling of Constructions of 1no. pump house, boundary wall, distribution line with FHTC for Lankapara 20no. Line for Augmentation of Lankapara TG for Lonkapara Hat Area PWSS Under Birpara Sub-Division, Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000449/2022-2023 | 2920/ALD | 19/01/2023 | 16/09/2023 | SUDDHYA SING LAMA | 40.15 | 32.23 | 80.26 | 51
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Distribution line for Lankapara Sukundi line and adjoining areas for Augmentation of Lankapara TG for Lonkapara Hat PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000483/2022-2023 | 3318/ALD | 13/03/2023 | 24/02/2025 | SHYAMAL ROY | 18.77 | 12.6 | 67.12 | 87
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Supply,deliver and installation of open well pumping machineries and allied works at CWR of Lankapara W/S SCHEME under NMD-II, in the dist. of Alipurduar | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000012/2023-2024 | 30/AMSD | 28/04/2023 | 18/05/2023 | SARKAR ELECTRIC | 6.6 | 6.6 | 100 | 0
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Laying of DI & HDPE pipeline, River and road crossing construction of valve chamber, community water tank and other misc. works for Lonkapara PWSS, Birpara Sub-Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000370/2023-2024 | 86/ALD | 10/01/2024 | 09/04/2024 | SUDDHYA SING LAMA | 27.7 | 0 | 0 | 0
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Laying of DI & HDPE pipeline, construction of valve chamber and other works for Tulshipara TG at Lonkapara PWSS, Birpara Sub-Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000366/2023-2024 | 82/ALD | 10/01/2024 | 24/05/2024 | SUBIR GHOSH | 6.78 | 3.19 | 46.99 | 10
13 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | New service connection charges for LANKAPARA HAT 20 NO LINE PWSS PH NO-1 |  |  | BILL/00736/2024-2025 | BP-194/24-25 | 09/07/2024 | 09/07/2024 | WBSEDCL | 5.07 | 0 | 0 | 0
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Route surveying and revalidation of Household data with digitization of LDS for Lankapara (Zone-I, Zone-II & Zone-III) PWSS under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000097/2025-2026 | 1181/ALD | 26/06/2025 | 26/07/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM | 6.65 | 0 | 0 | 0
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF LANKAPARA TG FOR LONKAPARA HAT AREA PIPED WATER SUPPLY SCHEME | SM/11767 | Augmentation | Laying of additional DI & HDPE pipeline, Construction of sluice valve chamber & other works at Tulshipara TG (under Lankapara TG) PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000523/2026-2027 | 1985/ALD | 17/08/2026 | 16/10/2026 | AVNI CONSTRUCTION | 13.72 | 0 | 0 | 0
Total | [13 empty] | 212.35 | 82.38 | 38.79