## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Soil investigation works for proposed overhead reservoir of KAIJALI BUSTI PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000339/2022-2023 | 2248/ALD | 21/11/2022 | 21/12/2022 | K S GROUP | 0.65 | 0.65 | 100 | 11
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Tubewell boring by ODEX-165 method of drilling, construction of Pump House, Boundary wall at proposed 4th TW site of Kaijali PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000004/2023-2024 | 07/ALD | 04/04/2023 | 02/08/2023 | PRITAM DAS | 17.41 | 16.17 | 92.85 | 100
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 1588/ALD | 14/09/2022 | 14/09/2022 | Resource Division | 30.75 | 0 | 0 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | QUATATION |  |  | BILL/02208/2023-2024 | BP-2023-24-484 | 12/12/2023 | 12/12/2023 | WBSEDCL | 5.11 | 0 | 0 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | QUOTATION |  |  | BILL/02209/2023-2024 | BP-2023-24-485 | 12/12/2023 | 12/12/2023 | WBSEDCL | 11.22 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Land development works, Construction of surface drain, pathway, and other allied works at Kaijali Busty 3rd tube well site with the Augmentation of Kaijili Busty PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE.(SM/11958) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000221/2024-2025 | 2274/ALD | 05/08/2024 | 04/10/2024 | KAMALESH ROY | 3.84 | 0.18 | 4.68 | 50
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Laying of new HDPE pipeline for interconnection in the distribution system and bridge/culvert crossing land developmentworks, construction of surface drain, pathway and other allied works in connection with the Augmentation of KAijali Basty PWSS (SM/11958) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000392/2024-2025 | 3958/ALD | 26/11/2024 | 25/01/2025 | MAHENDRA CHHETRI | 29.4 | 0 | 0 | 0
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Tube well Boring by ODEX-165 method of drilling at 3rd TWsite including laying Distribution system with new HDPE Pipeline (Part-A), Providing FHTC and other allied works for augmentation of KAIJALI BUSTY PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000331/2022-2023 | 2240/ALD | 21/11/2022 | 13/07/2024 | KAMALESH ROY | 70.16 | 60.09 | 85.64 | 68
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Construction of 200 cum OHR as per Departmental Design and drawing at KAIJALI BUSTY PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000353/2022-2023 | 2497/ALD | 13/12/2022 | 05/06/2024 | MAHENDRA CHHETRI | 68.63 | 66.32 | 96.64 | 70
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 3609/ALD | 24/10/2024 | 24/10/2024 | Resource Division | 11.11 | 0 | 0 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Kaijali Basty Water Supply Scheme TW No.- I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000893/2023-2024 | 2480/NMD-II | 11/08/2023 | 10/09/2023 | DIAMOND ELECTRICAL WORKS | 25.08 | 11.74 | 46.82 | 90
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Reparing of Pump House at 2nd TW site of Kaijali Basty PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000566/2024-2025 | 5382/ALD | 17/03/2025 | 16/05/2025 | TAPASH KUMAR BHOWMICK | 0.92 | 0 | 0 | 0
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Reparing of Pump House at Headwork site of Kaijali Basty PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000565/2024-2025 | 5381/ALD | 17/03/2025 | 16/05/2025 | TAPASH KUMAR BHOWMICK | 0.94 | 0 | 0 | 0
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Laying Rising Main, providing FHTC, Repairing existing Pipe line, Restoration of FHTC at 4th TW site and Gap filing in distribution system at Kaijali Busty PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000101/2025-2026 | 1186/ALD | 26/06/2025 | 09/09/2025 | RAMEN DEY & CO | 15.59 | 0 | 0 | 0
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Restoration of damaged FHTCs of Kaijali Busty PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000102/2025-2026 | 1187/ALD | 26/06/2025 | 10/08/2025 | RAMEN DEY & CO | 4 | 0 | 0 | 0
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Land development works, Construction of surface drain, pathway, and other allied works at Kaijali Busty 4th tube well site with the Augmentation of Kaijali Busty PWSS Under Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE.(SM/11958) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000220/2024-2025 | 2273/ALD | 05/08/2024 | 01/02/2025 | RAMEN DEY & CO | 4.28 | 4.24 | 98.95 | 100
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2025-2026 | 1564/ALD | 31/07/2025 | 31/07/2025 | Resource Division | 6.91 | 0 | 0 | 0
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2025-2026 | 1567/ALD | 31/07/2025 | 31/07/2025 | Resource Division | 6.91 | 0 | 0 | 0
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF KAIJALI BASTY WATER SUPPLY SCHEME | SM/11958 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kumargram Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000081/2025-2026 | 1049/ALD | 17/06/2025 | 13/04/2026 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 15
Total | [13 empty] | 405.4 | 159.39 | 39.32