## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Extension and replacement of damaged pipeline and providing house connection at Dakshin Sonapur Area under Sonapur PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000080/2021-2022 | 976/ALD | 13/09/2021 | 12/11/2021 | MADHAB SAHA | 44.48 | 43.57 | 97.97 | 17
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | River crossing for laying DI pipe line, Extension and replacement of damaged pipeline and providing FHTC at Sonapur and surrounding area of Sonapur PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000357/2021-2022 | 2236/ALD | 14/01/2022 | 15/03/2022 | M/S SIBU DEY AND CO | 38.07 | 34.93 | 91.75 | 91
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at Dakshin Kashigram area under Sonapur PWSS under Alipurduar Division, Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000366/2021-2022 | 2294/ALD | 24/01/2022 | 25/03/2022 | SASANKA ROY | 50.15 | 47.18 | 94.06 | 18
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Soil investigation work for Augmentaion of Dakshin Sonapur PWSS under Alipurduar Division PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000406/2022-2023 | 2791/ALD | 10/01/2023 | 09/02/2023 | MOYTEC | 0.95 | 0.95 | 100 | 0
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Construction of platform for FHTC laying of different dia. UPVC and DI pipe line at Dakshin Sonapur PWSS and adjoining mouzas under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division,JUNIOR ENGINEER | ORD/000320/2023-2024 | 2415/ALD | 09/11/2023 | 08/01/2024 | MADHAB SAHA | 31.16 | 6.37 | 20.43 | 15
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Providing FHTC from existing distribution system as per specification for Augmentation of DAKSHIN SONAPUR PWSS at Uttar Sonapur and adjoining moujas under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000345/2023-2024 | 2546/ALD | 28/11/2023 | 26/02/2024 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.34 | 0 | 0 | 0
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Providing FHTC from existing distribution system as per specification for Augmentation of DAKSHIN SONAPUR PWSS at Kumarpara and adjoining moujas under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000360/2023-2024 | 2746/ALD | 14/12/2023 | 12/02/2024 | KAMALESH ROY | 34 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT DAKSHIN SONAPUR WS SCHEME P/H NO.-VI |  |  | BILL/01456/2023-2024 | BP-2023-24-290 | 21/08/2023 | 21/08/2023 | WBSEDCL | 4.2 | 0 | 0 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT DAKSHIN SONAPUR W/S SCHEME P/H NO.-V |  |  | BILL/01455/2023-2024 | BP-2023-24-289 | 21/08/2023 | 21/08/2023 | WBSEDCL | 4.2 | 0 | 0 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Dakshin Sonapur Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/001099/2023-2024 | 2827/NMD-II | 11/10/2023 | 10/11/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 21.93 | 14.28 | 65.12 | 50
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Laying HDPE pipeline from Dakshin Sonapur aath mile bazaar to head work site due to widening of NH and providing FHTC at Dakshin Sonapur PWSS Area, Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000003/2023-2024 | 06/ALD | 04/04/2023 | 27/06/2024 | PINTU SAHA | 46.56 | 46.03 | 98.86 | 80
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Procurement of Laptop,Tab .Assemble Deskton Printer VC accessories and Other related accessories Tor all Permanent & contractual JE. all Assistant Engineer and Divisional Staff at Alipurduar PHED. |  |  | BILL/00098/2024-2025 | 77/24-25/PFMS | 21/06/2024 | 21/06/2024 | CYBERNET | 31.34 | 0 | 0 | 0
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Extension and replacement of damaged pipeline and providing house connection at Panchkolguri area under Sonapur PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000081/2021-2022 | 977/ALD | 13/09/2021 | 30/05/2025 | M/S JHA CONSTRUCTION | 43.59 | 40.35 | 92.57 | 60
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Laying of Different Dia pipeline And providing FHTC For Uttar Simlabari and adjoing area under Patlakhowa PWSS at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000121/2022-2023 | 1491/ALD | 05/09/2022 | 10/10/2024 | SHREE RANISATI ENTERPRISE | 100.02 | 0 | 0 | 30
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Construction of 700cum OHR for Augmentation of DAKSHIN SONAPUR Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER,RWS Alipurduar - I Block | ORD/000263/2022-2023 | 1495/ALD | 05/09/2022 | 20/08/2025 | SHREE RANISATI ENTERPRISE | 123.17 | 52.09 | 42.29 | 5
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. Part-1 | Alipurduar RWS | JUNIOR ENGINEER | ORD/000261/2022-2023 | 1493/ALD | 05/09/2022 | 07/04/2025 | MADHAB SAHA | 34.59 | 0 | 0 | 27
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. Part-2 | Alipurduar RWS | JUNIOR ENGINEER,RWS Alipurduar - I Block | ORD/000262/2022-2023 | 1494/ALD | 05/09/2022 | 20/08/2025 | KAJAL KUMAR DE | 34.44 | 0 | 0 | 15
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Boring of Tube Well, Construction of Pump House, Boundary Wall, Laying Of Rising Main, Distribution System for Augmentation of Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. (2nd call) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000480/2022-2023 | 3197/ALD | 27/02/2023 | 15/08/2025 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 171.88 | 83.31 | 48.47 | 35
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01/02/2023 to 30/04/2023) | Alipurduar Sadar Sub Division,HQ-A.E | Birpara Sub Division | ORD/000567/2022-2023 | 2953/ALD | 24/01/2023 | 24/04/2023 | NIRANJAN KIRTANIA | 0.5 | 0.5 | 100 | 0
21 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Continuation of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2024 to 29.02.2024) | Birpara A.E | Birpara Sub Division | ORD/000546/2023-2024 | 2907/ALD | 29/12/2023 | 29/02/2024 | PARITOSH SUTRADHAR | 0.8 | 0.77 | 96.77 | 0
22 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Laying of distribution line with HDPE, UPVC & CI/DI Pipes at Kumarpara & adjoining areas and others allied works for Augmentation of Dakshin Sonapur PWSS within Alipurduar-I Block under Alipurduar Division, PHE DTE. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000055/2025-2026 | 706/ALD | 22/05/2025 | 05/08/2025 | S.D. PROJECT | 150.21 | 0 | 0 | 0
23 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
24 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Dakshin Sonapur Water Supply Scheme TW No.-III (Additional) under NMD-II,PHE.Dte,Alipurduar. | HQ-A.E | JUNIOR ENGINEER | ORD/000057/2025-2026 | 785/ALD | 30/05/2025 | 29/06/2025 | DILIP MAHATO (OPC) PRIVATE LIMITED | 11.09 | 0 | 0 | 0
25 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Repairing of pump house at 2nd site of Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000205/2025-2026 | 2352/ALD | 10/11/2025 | 09/01/2026 | DIPAK DAS | 2.29 | 0 | 0 | 0
26 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Road crossing and laying of different dia pipeline for Dakshin Sonapur WSS under Alipurduar-I Block under Alipurduar Division, P.H.E. Dte. | Alipurduar RWS | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000397/2022-2023 | 2664/ALD/ | 22/12/2022 | 23/08/2024 | M/S AMIT KUMAR GUPTA | 31.75 | 28.1 | 88.5 | 88
27 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Fabrication,Erection of Signage (135 nos) of Pump house/OHR site democration with in Alipurduar-II and Kalchini Block for Different PWSS of JJM Project Under Alipurduar Division P.H.E.Dte. | HQ-A.E | RWS Kumargram Block | ORD/000355/2024-2025 | 3442/ALD | 27/09/2024 | 11/04/2025 | M/S SARKAR & CO | 14.84 | 6.82 | 45.96 | 100
28 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Sinking of Big dia Tube Well (250 x 200 mm dia) by R.C. drilling for Aug. of Dakshin Sonapur PWSS within Alipurduar-I Block of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/11970) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000235/2024-2025 | 2295/ALD | 07/08/2024 | 02/03/2025 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 20.72 | 0 | 0 | 100
29 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Painting of Old OHR at Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000443/2024-2025 | 5046/ALD | 17/02/2025 | 18/04/2025 | SANKAR ROY | 3.78 | 0 | 0 | 100
30 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | New Service Connection Charges for Dashkin Sonapur P/H NO-3 Under NMD-II in the dist. of Alipurduar |  |  | BILL/00616/2024-2025 | 332/24-25/PFMS | 21/03/2025 | 21/03/2025 | WBSEDCL | 5.71 | 0 | 0 | 0
31 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at Uttar Kashigram area under Sonapur PWSS under Alipurduar Division, Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000367/2021-2022 | 2295/ALD | 24/01/2022 | 04/03/2026 | NARENDRA BHADANI. | 45.29 | 24.47 | 54.03 | 18
32 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | CONSTRUCTION OF PUMP HOUSE & BOUNDARY WALL FOR ADDITIONAL TUBEWELL FOR PROVIDING FHTC AND LAND DEVELOPMENT AT HW SITE & 2ND SITE FOR AUGMENTATION OF DAKSHIN SONAPUR PWSS. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000026/2025-2026 | 435/ALD | 30/04/2025 | 24/02/2026 | TAPASH DAS | 16.07 | 0 | 0 | 60
33 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF DAKSHIN SONAPUR WATER SUPPLY SCHEME | SM/11970 | Augmentation | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-I Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | HQ-A.E | JUNIOR ENGINEER,RWS Kalchini Block | ORD/000082/2025-2026 | 1050/ALD | 17/06/2025 | 13/04/2026 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 15
Total | [13 empty] | 1316.62 | 429.72 | 32.64