## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 219/ALD | 03/05/2023 |  | Resource Division | 13.81 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 | New | Soil investigation works for proposed overhead reservoir of PHASKHAWA TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000316/2022-2023 | 2225/ALD | 21/11/2022 | 21/12/2022 | K S GROUP | 0.65 | 0.65 | 100 | 0
3 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 | New | QUOTATION FOR NSC AT PHASKHAWA PH NO-I |  |  | BILL/00422/2023-2024 | BP-2023-24-153 | 01/06/2023 |  | WBSEDCL | 1.31 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 | New | QUOTATION FOR NSC AT PHASKHAWA TG PH NO-II |  |  | BILL/00423/2023-2024 | BP-2023-24-152 | 01/06/2023 |  | WBSEDCL | 1.31 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 | New | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at 2nd site of Phaskhawa TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000324/2022-2023 | 2233/ALD | 21/11/2022 | 19/02/2023 | RAMEN DEY & CO | 9.7 | 9.17 | 94.52 | 94
6 | ALIPURDUAR | Kumargram | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 | New | Supply of CIDF & CISS Pipes and specials for Phashawa TG WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000234/2023-2024 | 1596/ALD | 25/08/2023 | 24/09/2023 | DILIP MAHATO | 5.64 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Phaskhawa TG water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000678/2023-2024 | 2076/NMD-II | 26/07/2023 | 25/08/2023 | M/S PARITOSH BHOWMICK & CO. | 18.54 | 4.22 | 22.78 | 50
8 | ALIPURDUAR | Kumargram | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 | New | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at Head work site of Phaskhawa TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000322/2022-2023 | 2231/ALD | 21/11/2022 | 19/02/2023 | SANKAR ROY | 13.56 | 5.41 | 39.88 | 65
9 | ALIPURDUAR | Kumargram | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 | New | Construction of Pump House at Head Work site and providing FHTC and other allied works for Phaskhawa TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000319/2022-2023 | 2228/ALD | 21/11/2022 | 19/07/2023 | PRITAM DAS | 9.88 | 6.8 | 68.86 | 51
10 | ALIPURDUAR | Kumargram | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 | New | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 200 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for PHASKHAWA TEA GARDEN PWSS under Alipurduar Division, PHE Dte | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000456/2022-2023 | 2977/ALD | 02/02/2023 | 01/08/2023 | DILIP MAHATO | 133.11 | 75.94 | 57.05 | 61
11 | ALIPURDUAR | Kumargram | Alipurduar Division | PHASKHAWA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/11992 | New | Tube well Boring by ODEX-165 method of drilling at 2nd TW Site, Construction of Pump house at 2nd site, laying of Rising Main and delivery line connection, providing FHTC and other allied works for Phaskhawa Tea Garden PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000329/2022-2023 | 2238/ALD | 21/11/2022 | 21/03/2023 | ASHOK SAPKOTA | 22.24 | 13.42 | 60.32 | 100
Total | [13 empty] | 229.75 | 115.62 | 50.32