## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Tube well Boring by ODEX-165 method of drilling at 2nd TW site, Construction of Pump house and Boundary wall at 2nd site, Laying of Rising and delivery line connection, Providing FHTC and other allied works for KOHINUR TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000326/2022-2023 | 2235/ALD | 21/11/2022 | 21/03/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 96.96 | 53.89 | 55.58 | 56
2 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Providing balance FHTC for KOHINUR TG PWSS (PART-II) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000243/2023-2024 | 1789/ALD | 29/08/2023 | 28/10/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 16.73 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Soil investigation works for proposed overhead reservoir of KOHINUR TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000314/2022-2023 | 2223/ALD | 21/11/2022 | 21/12/2022 | K S GROUP | 0.65 | 0.65 | 100 | 16
4 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Tubewell boring by ODEX-165 method of drilling, construction of Pump House, Boundary Wall at Proposed 3rd TW site of Kohinur TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000039/2023-2024 | 370/ALD | 18/05/2023 | 15/09/2023 | DILIP MAHATO | 17.39 | 17.27 | 99.28 | 100
5 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 218/ALD | 03/05/2023 | 03/05/2023 | Resource Division | 35.18 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Quotation for NSC at P/H No.III under Kohinoor TG W/S/S |  |  | BILL/00601/2023-2024 | BP-2023-24-174 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.31 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Quotation for NSC at P/H No.I under Kohinoor TG W/S/S |  |  | BILL/00599/2023-2024 | BP-2023-24-172 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.31 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Quotation for NSC at P/H No.II under Kohinoor TG W/S/S |  |  | BILL/00600/2023-2024 | BP-2023-24-173 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.31 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Providing balance FHTC for KOHINUR TG PWSS (PART-I) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000250/2023-2024 | 1852/ALD | 04/09/2023 | 03/11/2023 | TAPASH DAS | 16.73 | 13.52 | 80.83 | 81
10 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Laying of HDPE/DI pipe line near Dangi Aashram Ground and Kohinur Gram Panchayat office area for interconnection in the distribution system and bridge /culvert crossing under KOHINUR TEA GARDEN PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/12113) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000393/2024-2025 | 4179/ALD | 03/12/2024 | 01/02/2025 | MAHAPRABHU ENTERPRISE | 61.89 | 0 | 0 | 0
11 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kohinur TG water supply scheme, TW no I,II and III of under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000757/2023-2024 | 2340/NMD-II | 01/08/2023 | 31/08/2023 | ALPHA ENTERPRISE | 32.93 | 32.57 | 98.9 | 70
12 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Kohinur TG Water Supply Scheme under Alipurduar Division P.H.E. Dte.(SM/12113) | Alipurduar Sadar Sub Division | Birpara Sub Division,RWS Alipurduar - II Block | ORD/000468/2023-2024 | 674/ALD | 06/03/2024 | 03/08/2024 | BHAGWATI BHUJEL | 11.36 | 11.33 | 99.75 | 80
13 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Material Requisition To Resource Division |  |  | RTOR000052/2024-2025 | 4272/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 12.78 | 0 | 0 | 0
14 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 400 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for KOHINUR TEA GARDEN PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000458/2022-2023 | 2979/ALD | 02/02/2023 | 28/01/2024 | DILIP MAHATO | 237.14 | 203.99 | 86.02 | 86
15 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Laying of HDPE/DI pipe line near kohinur TG factory area for interconnection in the distribution system and bridge /culvert crossing , Construction of Pump House, Boundary Wall at Head work site of KOHINUR TEA GARDEN PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/12113). | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000229/2024-2025 | 2282/ALD | 05/08/2024 | 02/04/2025 | DILIP MAHATO | 60.91 | 13.08 | 21.48 | 95
16 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Laying of HDPE/DI pipe line near Dangi Bazar area for interconnection in the distribution system and bridge /culvert crossing under KOHINUR TEA GARDEN PWSS , Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/12113) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000227/2024-2025 | 2280/ALD | 05/08/2024 | 02/04/2025 | JAYDAB ADHIKARI | 26.67 | 0 | 0 | 85
17 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Continuation of work of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte. (from 01.01.2025 to 31.03.2025) | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000459/2024-2025 | 4554/ALD | 30/12/2024 | 30/03/2025 | MATRI ENTERPRISE | 1.2 | 0 | 0 | 0
18 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
19 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | KOHINUR TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/12113 | New | Supply of CIDF & CISS Pipes and specials for Kohinur TG WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division,RWS Alipurduar - II Block | ORD/000231/2023-2024 | 1600/ALD | 25/08/2023 | 16/02/2025 | DILIP MAHATO | 6.76 | 0 | 0 | 85
Total | [13 empty] | 713.57 | 346.31 | 48.53