## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of Baniadabri and Garokhota Area under SAMUKTALA WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000279/2022-2023 | 1665/ALD | 19/09/2022 | 18/03/2023 | GOUTAM KUMAR DAS | 101.2 | 0 | 0 | 47
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of SAMUKTALA ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000276/2022-2023 | 1662/ALD | 19/09/2022 | 18/03/2023 | M/S SSB CONSTRUCTION CO. | 100.42 | 0 | 0 | 48
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of Baniadabri and Samuktala Bazar Area under SAMUKTALA WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000278/2022-2023 | 1664/ALD | 19/09/2022 | 18/03/2023 | DILIP MAHATO | 100.58 | 0 | 0 | 46
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Boundary wall at 3rd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000267/2022-2023 | 1666/ALD | 19/09/2022 | 19/10/2022 | PRITAM DAS | 4.74 | 0 | 0 | 47
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Pump House at 4th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000271/2022-2023 | 1672/ALD | 19/09/2022 | 18/11/2022 | PROJIT HALDER | 4.77 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying distribution pipeline with UPVC pipe of Samuktala Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000280/2022-2023 | 1660/ALD | 19/09/2022 | 18/11/2022 | LONGLAST PIPES (INDIA)PVT.LTD. | 97.26 | 0 | 0 | 50
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying distribution system with new UPVC/DI pipeline along with rising and delivery line connection, providing FHTC and other allied works for Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000394/2022-2023 | 2659/ALD | 22/12/2022 | 21/04/2023 | ESCON INDIA | 90.53 | 0 | 0 | 50
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying of UPVC pipeline for filling of Gap in distribution system Samuktala Zone-I PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000489/2022-2023 | 3321/ALD | 13/03/2023 | 12/05/2023 | CHANDAN KIRTONIA | 5.37 | 0 | 0 | 0
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Cons. Of pathway, surface drain and chatal, Installation of Paver block, land development along with the other allied works at Samuktala Zone-II H/W, 2nd site and 3rd Tube well Site under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000333/2023-2024 | 2519/ALD | 24/11/2023 | 23/01/2024 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 23.26 | 0 | 0 | 0
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Soil investigation work at 3 different places of Samuktala within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000266/2022-2023 | 1657/ALD | 19/09/2022 | 19/10/2022 | ASIS ENTERPRISE | 3.65 | 0 | 0 | 50
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Pump House at 3rd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000270/2022-2023 | 1671/ALD | 19/09/2022 | 18/11/2022 | SWADESH DEV | 4.75 | 0 | 0 | 100
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Pump House at 2nd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000293/2022-2023 | 1670/ALD | 19/09/2022 | 18/11/2022 | M/S SADHAN SAHA & CO. | 4.76 | 0 | 0 | 100
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | 5 nos Tube well boring by ODEX - 165 Method of drilling for the works of augmentation of SAMUKTALA PWSS under Alipurduar Division ,PHE Dte | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000342/2022-2023 | 2221/ALD | 21/11/2022 | 21/12/2022 | S.G. CONSTRUCTION | 32.14 | 0 | 0 | 50
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Boundary wall at 4th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000273/2022-2023 | 1667/ALD | 19/09/2022 | 03/11/2022 | DHANENDRA SARKAR | 4.77 | 0 | 0 | 100
15 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR SAMUKTALA ZONE -III P/H NO.I |  |  | BILL/00785/2023-2024 | BP-2023-24-219 | 13/07/2023 | 13/07/2023 | WBSEDCL | 1.54 | 0 | 0 | 0
16 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR SAMUKTALA ZONE -III P/H NO.II |  |  | BILL/00786/2023-2024 | BP-2023-24-220 | 13/07/2023 | 13/07/2023 | WBSEDCL | 1.54 | 0 | 0 | 0
17 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | New Service Connection Charge For Samuktala Z-I P/H No.I |  |  | BILL/00902/2023-2024 | BP-2023-24-222 | 13/07/2023 | 13/07/2023 | WBSEDCL | 1.54 | 0 | 0 | 0
18 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | NEW SEVICE CONNECTION CHARGES FOR SAMUKTALA PWSS ZONE-IIP/H NO.I |  |  | BILL/00741/2023-2024 | BP-2023-24-218 | 13/07/2023 | 13/07/2023 | WBSEDCL | 1.54 | 0 | 0 | 0
19 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | New Service Connection Charge For Samuktala Z-I P/H NO-II |  |  | BILL/00901/2023-2024 | BP-2023-24-221 | 13/07/2023 | 13/07/2023 | WBSEDCL | 1.54 | 0 | 0 | 0
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying distribution system with new UPVC pipeline, providing FHTC and other allied works for Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000356/2022-2023 | 2501/ALD | 13/12/2022 | 12/04/2023 | MADHAB SAHA | 93.21 | 0 | 0 | 49
21 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of SAMUKTALA water supply scheme, TW no I AND II OF ZONE-I , TW no I AND II OF ZONE-II , TW no I AND II OF ZONE-III under Jal Jeevan Mission under NMD-II, PHE Dte.APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000002/2023-2024 | 759/NMD-II | 04/04/2023 | 04/05/2023 | AHALYA ENGINEERING WORKS | 63.4 | 0 | 0 | 40
22 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of pathway, surface drain and chatal, installation of paver block, land development along with the others allied works at Samuktala Zone-I head work site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000197/2023-2024 | 1495/ALD | 16/08/2023 | 15/10/2023 | DIPAK DAS | 13.04 | 0 | 0 | 25
23 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying of rising main and delivery line connection, construction of boundary wall at headwork site of Samuktala Zone-I PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000340/2023-2024 | 2541/ALD | 28/11/2023 | 22/11/2024 | DIPAK DAS | 28.74 | 0 | 0 | 100
24 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing in connection with the FHTC, fixing of FHTC by means of PCC concrete block fixing of FHTC by mean of PCC concrete block at Samuktalata Zone-III PWSS under Alipurduar Division, PHE Dte. (SM/12561) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000380/2024-2025 | 3774/ALD | 13/11/2024 | 11/02/2025 | DAS CONSTRUCTION | 60.38 | 0 | 0 | 0
25 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Boundary wall at 5th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000268/2022-2023 | 1668/ALD | 19/09/2022 | 16/06/2023 | ROY & PANDIT CONSTRUCTIONS | 4.76 | 0 | 0 | 100
26 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Pump House at 1st TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000269/2022-2023 | 1669/ALD | 19/09/2022 | 18/11/2022 | KOUSHIK BHOWMICK | 4.77 | 0 | 0 | 95
27 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Pump House at 5th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000272/2022-2023 | 1673/ALD | 19/09/2022 | 18/11/2022 | CHITTA RANJAN DEY | 4.75 | 0 | 0 | 100
28 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of 400cum OHR for SAMUKTALA ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000274/2022-2023 | 1659/ALD | 19/09/2022 | 18/03/2023 | DILIP MAHATO | 77.32 | 0 | 0 | 100
29 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of 350cum OHR for SAMUKTALA ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000275/2022-2023 | 1661/ALD | 19/09/2022 | 18/03/2023 | MATARA CONSTRUCTION CO | 71.41 | 0 | 0 | 100
30 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Land development works at headwork site and laying of new UPVC/DI pipeline for filling gap in distribution system Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000488/2022-2023 | 3320/ALD | 13/03/2023 | 12/05/2023 | BHAGWATI BHUJEL | 9.19 | 0 | 0 | 100
31 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Repairing of HW Site Boundary Wall (15M) Samuktala WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000556/2022-2023 | 3501/ALD | 23/03/2023 | 21/07/2023 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 2.14 | 0 | 0 | 100
32 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of boundary wall (remaining portion) at Headwork site under Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000289/2023-2024 | 1903/ALD | 07/09/2023 | 01/09/2024 | SWAPAN MALAKAR | 6 | 0 | 0 | 100
33 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Tube well boring by ODEX-165 Method of drilling, Construction of Pump House, Boundary wall at proposed 6th site of SAMUKTALA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000324/2023-2024 | 2421/ALD | 09/11/2023 | 03/11/2024 | DULAL DAS | 17.57 | 0 | 0 | 100
34 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Samuktala Water Supply Scheme under Alipurduar Division P.H.E. Dte. (SM/12561) | Alipurduar Sadar Sub Division | Birpara Sub Division,RWS Alipurduar - II Block | ORD/000467/2023-2024 | 673/ALD | 06/03/2024 | 05/04/2024 | BHAGWATI BHUJEL | 11.36 | 0 | 0 | 15
35 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Fabrication,Erection of Signage (127 nos) of Pump house/OHR site democration with in Alipurduar-I Block for Different PWSS of JJM Project Under Alipurduar Division P.H.E.Dte. | HQ-A.E | RWS Kumargram Block | ORD/000356/2024-2025 | 3443/ALD | 27/09/2024 | 12/10/2024 | M/S SARKAR & CO | 13.95 | 0 | 0 | 100
36 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA |  |  | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 14/11/2024 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0 | 0
37 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of 100cum. OHR for SAMUKTALA ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000265/2022-2023 | 1658/ALD | 19/09/2022 | 02/11/2025 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 43.9 | 0 | 0 | 100
38 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying distribution system with new UPVC pipeline, providing FHTC and other allied works for Samuktala Zone-II PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000355/2022-2023 | 2500/ALD | 13/12/2022 | 12/04/2023 | TAPASH KUMAR BHOWMICK | 88.46 | 0 | 0 | 50
39 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing in connection with the FHTC, fixing of FHTC by means of PCC concrete block fixing of FHTC by mean of PCC concrete block at Samuktalata Zone-II PWSS under Alipurduar Division, PHE Dte. (SM/12561) | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000352/2024-2025 | 3422/ALD | 26/09/2024 | 24/05/2025 | KAMALESH ROY | 75.37 | 0 | 0 | 0
40 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
41 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Reparing of Pump House no 2 at HW site of SAMUKTALA PWSS Under Alipurduar Division PHE DTE.(2nd call) |  |  | ORD/000611/2024-2025 | 5601/ALD | 27/03/2025 | 26/05/2025 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.96 | 0 | 0 | 0
42 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Interconnection of distribution system by laying of DI and HDPE pipes along with bridge/culvert crossing and other allied works at Shrinathpur TG Adjacent to Samuktala PWSS (Zone-I) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000462/2024-2025 | 5288/ALD | 07/03/2025 | 06/05/2025 | DEBAJYOTI SUTRADHAR | 18.28 | 0 | 0 | 0
43 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Supply and installation of sign board at different PWSS site of Alipurduar-II Block under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000071/2025-2026 | 969/ALD | 12/06/2025 | 27/07/2025 | HARI CONSTRUCTION | 4.92 | 0 | 0 | 0
44 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Restoration of FHTCs and withdrawing and relaying a pipeline (125 mm) at Patotola area at 5th site Samuktala PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - II Block | ORD/000052/2025-2026 | 678/ALD | 21/05/2025 | 05/07/2025 | DULAL DAS | 4.5 | 0 | 0 | 0
45 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Repairing of Pump House no1 at HW site of SAMUKTALA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000153/2025-2026 | 1590/ALD | 31/07/2025 | 29/09/2025 | PRITAM DAS | 0.97 | 0 | 0 | 0
46 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of SAMUKTALA ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000277/2022-2023 | 1663/ALD | 19/09/2022 | 18/03/2023 | MATARA CONSTRUCTION CO | 101.06 | 0 | 0 | 100
47 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying distribution system with new UPVC/DI pipeline along with rising and delivery line connection, providing FHTC and others allied works for Samuktala Zone-II PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000393/2022-2023 | 2658/ALD | 22/12/2022 | 09/06/2025 | HARIDAS GHOSH | 88.71 | 0 | 0 | 48
Total | [13 empty] | 1633.41 | 0 | 0