## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | SM/12754 | New | Construction of Tube Well, Pump House, Boundary Wall, OHR, Laying Of Rising Main, Distribution System including soil test and providing FHTC for Naothoartari PWSS Under Alipurduar Division, PHE Dte. | Alipurduar RWS,HQ-A.E | JUNIOR ENGINEER | ORD/000577/2022-2023 | 3638/ALD | 31/03/2023 | 11/09/2026 | CHINMOY BHATTACHARJEE | 267.68 | 164.49 | 61.45 | 40
2 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | SM/12754 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Naothoatari water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000815/2023-2024 | 2389/NMD-II | 09/08/2023 | 01/04/2025 | MUSTAFI CONCERN | 18.11 | 0 | 0 | 90
3 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | SM/12754 | New | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 3045/ALD | 08/02/2023 | 08/02/2023 | Resource Division | 7.53 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | SM/12754 | New | QUOTATION FOR NEW SERVICE CONNECTION AT NATHUATARI PWSS P/H NO. II |  |  | BILL/01450/2023-2024 | BP-2023-24-285 | 21/08/2023 | 21/08/2023 | WBSEDCL | 5.45 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | SM/12754 | New | QUOTATION FOR NEW SERVICE CONNECTION AT NATHUATARI PWSS P/H NO.I |  |  | BILL/01449/2023-2024 | BP-2023-24-294 | 21/08/2023 | 21/08/2023 | WBSEDCL | 5.92 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | SM/12754 | New | "Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Augmentation of Nathoatari Water Supply Scheme (SM/12754) of Alipurduar-I Block under Alipurduar Division P.H.E. Dte. " | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000524/2023-2024 | 843/ALD | 14/03/2024 | 13/09/2024 | MAKALI ENGINEERING CORPORATION | 14.43 | 14.43 | 100 | 25
7 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | SM/12754 | New | Material Requisition To Resource Division |  |  | RTOR000041/2024-2025 | 4256/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 9.16 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | SM/12754 | New | Gap Filling of distribution line, land development at Pump House and others allied works for NAOTHOARTARI PWSS within Alipurduar Block-I under Alipuduar Division PHE.Dte. | HQ-A.E | JUNIOR ENGINEER | ORD/000075/2025-2026 | 973/ALD | 12/06/2025 | 05/09/2026 | CHINMOY BHATTACHARJEE | 42.38 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | SM/12754 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar-I Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001208/2024-2025 | 822/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | NAOTHOARTARI PIPED WATER SUPPLY SCHEME | SM/12754 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
Total | [13 empty] | 1125.75 | 178.92 | 15.89