## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF SAMUKTALA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12909 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for Alipurduar Division(HQ), PHE Dte. | HQ-A.E |  | ORD/000423/2022-2023 | 2826/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0 | 0 | 100
2 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF SAMUKTALA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12909 | Support-WQMSP | Calibration of necessary Instrument, Glasswares & as per ISO/IEC 17025:2017 for Birpara Sub District Lab & Samuktala Sub District Lab under Alipurduar Division. PHE. Dte. | Alipurduar RWS | Alipurduar Sub Division | ORD/000569/2022-2023 | 3631/ALD | 31/03/2023 | 30/04/2023 | LAB SOLUTION | 0.93 | 0 | 0 | 100
3 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF SAMUKTALA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12909 | Support-WQMSP | Continuation for the work of Calibration of laboratory instrument/equipment related to NABL Recognition of Samuktala Sub District Laboratory and Birpara Sub District Laboratory as per ISO/IEC 17025- 2017 and procurement of Chemicals/Reagents/Water sample testing equipment/Kits for 03 No's Laboratories under Alipurduar Division, PHE. Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000210/2025-2026 | 2376/ALD | 12/11/2025 | 11/01/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 8.12 | 0 | 0 | 0
Total | [13 empty] | 9.68 | 0 | 0