## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF BIRPARA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12910 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for PHE Office Conferrence Room (left side) under Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000424/2022-2023 | 2827/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0 | 0 | 100
2 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF BIRPARA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12910 | Support-WQMSP | Procurement of chemical and glasswares for all laboratories under Alipurduar Division, PHE Dte. | Alipurduar RWS |  | ORD/000426/2022-2023 | 2829/ALD | 11/01/2023 | 26/01/2023 | DULAL MAJUMDER | 0.49 | 0 | 0 | 100
3 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF BIRPARA SUB DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12910 | Support-WQMSP | Procurement of necessary Chemical for Regular water sample testing purpose of all Laboratories Under Alipurduar Division PHE DTE. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000136/2025-2026 | 1573/ALD | 31/07/2025 | 30/08/2025 | CHANDAN DAS | 0.11 | 0 | 0 | 0
Total | [13 empty] | 1.24 | 0 | 0