## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12911 | Support-WQMSP | Providing consultancy services including calibration of measuring instruments for NABL Accreditation of Alipuduar District water testing Laboratory (Asper ISO-17025 Protocol) under Alipurduar Division: P.H.E. Dte. | Alipurduar RWS |  | ORD/000074/2021-2022 | 873/ALD | 02/09/2021 | 08/09/2021 | INSTITUTE OF APPLIED QUALITY MANAGEMENT | 3.31 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12911 | Support-WQMSP | Supply, delivery and Installation of split type Air Conditioner for PHE Office Conferrence Room (right side) under Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000425/2022-2023 | 2828/ALD | 11/01/2023 | 18/01/2023 | BETTER LIFE | 0.64 | 0 | 0 | 100
3 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12911 | Support-WQMSP | Procurement of necessary glasswares for water sample testing as per NABL scope and routine tests for all laboratories under Alipurduar Division, PHE Dte. | Alipurduar RWS | Alipurduar Sub Division | ORD/000159/2023-2024 | 963/ALD | 12/07/2023 | 11/08/2023 | LAB SOLUTION | 1.48 | 0 | 0 | 100
4 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12911 | Support-WQMSP | Instruments procurement related to NABL accredititation/recognition works & smooth functioning of all laboratories as per ISO/IEC 17025: 2017 Under Alipurduar Division, P.H.E Dte. | Alipurduar RWS | Alipurduar Sub Division | ORD/000191/2023-2024 | 1467/ALD | 16/08/2023 | 15/10/2023 | LAB SOLUTION | 8.33 | 0 | 0 | 60
5 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12911 | Support-WQMSP | Procurement of reagents/chemicals for water sample testing by NABL laboratories of Alipurduar Div |  |  | BILL/00170/2024-2025 | 113/24-25/PFMS | 29/07/2024 | 29/07/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 8.69 | 0 | 0 | 0
6 | ALIPURDUAR |  | Alipurduar Division | PROCUREMENT OF CHEMICALS,CRM,GLASSWARE,INSTRUMENT & EQUIPMENT WITH MISCELLANEOUS ITEMS FOR INFRASTRUCTURE DEVELOPEMENT OF ALIPURDUAR DISTRICT LABORATORY FOR NABL SET-UP UNDER ALIPURDUAR DIVISION, P.H.E. DTE., 2022 | SM/12911 | Support-WQMSP | PROCUREMENT OF NABL RELATED CONSUMABLES FOR TESTING LAB SUPPLY AND DELIVERY MATERIALS |  |  | BILL/00551/2023-2024 | 21/24-25/PFMS | 21/05/2024 | 21/05/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 6.96 | 0 | 0 | 0
Total | [13 empty] | 29.4 | 0 | 0