## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1274/ALD | 11/08/2023 | 11/08/2023 | Resource Division | 34.39 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-I,Z-II |  |  | BILL/00059/2023-2024 | BP-2023-24-54 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.37 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-I,Z-I |  |  | BILL/00060/2023-2024 | BP-2023-24-53 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.37 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-II,Z-II |  |  | BILL/00058/2023-2024 | BP-2023-24-52 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.37 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KADAMBINI TG TW NO-II,Z-I |  |  | BILL/00061/2023-2024 | BP-2023-24-55 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.37 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Kadambini water supply scheme, TW no I and II of Zone-II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000854/2023-2024 | 2437/NMD-II | 11/08/2023 | 10/09/2023 | A.G ENTERPRISE | 18.46 | 17.16 | 92.98 | 90
7 | ALIPURDUAR | Falakata | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | "Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Kadambini TG Water Supply Scheme (SM/13239) of Falakata Block under Alipurduar Division P.H.E. Dte. " | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000526/2023-2024 | 845/ALD | 14/03/2024 | 13/04/2024 | MANSAROVAR CASTING | 13.2 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Continuation work order for the work of "Sinking of Rig bore T/W (4nos.) by Reverse Rotary method of drilling, cons. of 100 cum. OHR (2nos), cons. of P/H and B/W, Rising main, distribution line and providing FHTC at H/W and 2nd site inclu. Soil testing for KADAMBINI TG PWSS (ZONE-I and ZONE-II) under Birpara Sub-Division, Alipurduar Division, PHE Dte." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/5/2024-EE(ALI_D) SEC-DPHE (Computer No-973264)) | Birpara A.E | RWS Falakata Block | ORD/000199/2024-2025 | 1913/ALD | 26/06/2024 | 25/08/2024 | DILIP MAHATO | 14.57 | 14.37 | 98.65 | 90
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Additional Quotation for New Service connection charges for Kadambini T.G PWSS, Zone-I,P/H No-I |  |  | BILL/02622/2023-2024 | BP-2023-24-588 | 02/02/2024 | 02/02/2024 | WBSEDCL | 11.92 | 0 | 0 | 0
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | ADDITIONAL QUOTATION FOR NEW SERVICE CONNECTION CHARGES FOR KADAMBINI T.G PWSS, ZONE-I,P/HNO-II |  |  | BILL/02750/2023-2024 | BP-2023-24-621 | 20/02/2024 | 20/02/2024 | WBSEDCL | 5.15 | 0 | 0 | 0
11 | ALIPURDUAR | Falakata | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Sinking of Rig bore T/W (4nos.) by Reverse Rotary method of drilling, cons. of 100 cum. OHR (2nos), cons. of P/H and B/W, Rising main, distribution line and providing FHTC at H/W and 2nd site inclu. Soil testing for KADAMBINI TG PWSS (ZONE-I and ZONE-II) under Birpara Sub-Division, Alipurduar Division, PHE Dte | Birpara A.E | RWS Falakata Block | ORD/000430/2022-2023 | 2857/ALD | 17/01/2023 | 09/06/2025 | DILIP MAHATO | 498.42 | 452.83 | 90.85 | 95
12 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Continuation order for Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II, PHE Dte. |  |  | ORD/000565/2024-2025 | 578/AMSD | 25/10/2024 | 25/12/2024 | MUSTAFI CONCERN | 0.75 | 0 | 0 | 0
13 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Solarization of grid connected pumping installation at Different PWSS at Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001207/2024-2025 | 821/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
14 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Yard lighting arrangement at Head Work Site for Different PWSS (KADAMBINI TG and Others) under JJM in the BLOCK: Falakata, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000137/2025-2026 | 1346/NMD-II | 19/06/2025 | 19/07/2025 | M/S SAJAHAN CHOWDHURY | 23.98 | 0 | 0 | 0
15 | ALIPURDUAR | Falakata | Northern Mechanical Division II | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
16 | ALIPURDUAR | Falakata | Alipurduar Division | KADAMBINI TEA GARDEN AREA PIPED WATER SUPPLY SCHEME | SM/13239 | New | Restoration of DI pipe crossing near CHOR TORSHA and other repair works in Banshidharpur area under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000035/2023-2024 | 366/ALD | 18/05/2023 | 17/06/2023 | NARENDRA BHADANI. | 1.42 | 0 | 0 | 100
Total | [13 empty] | 1382.85 | 484.36 | 35.03