## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PASCHIM CHENGMARI PWSS PH NO-II |  |  | BILL/00034/2023-2024 | BP-2023-24-27 | 27/04/2023 | 27/04/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PASCHIM CHENGMARI PWSS PH NO-I |  |  | BILL/00033/2023-2024 | BP-2023-24-14 | 27/04/2023 | 27/04/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Alipurduar Division | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 | New | Providing balance FHTC for PASCHIM CHENGMARI PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000248/2023-2024 | 1590/ALD | 25/08/2023 | 23/11/2023 | ANKIT SARKAR | 1.66 | 0 | 0 | 90
4 | ALIPURDUAR | Kumargram | Alipurduar Division | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 | New | Laying of new UPVC/DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, land development works, construction of surface drain, pathway, supply of CIDF specials and other allied works in connection with the Paschim Chengmari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000337/2023-2024 | 2523/ALD | 24/11/2023 | 20/08/2024 | M/S SSB CONSTRUCTION CO. | 83.57 | 0 | 0 | 57
5 | ALIPURDUAR | Kumargram | Alipurduar Division | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 133/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 5.72 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 | New | Cons. of P/H and T/W Boring by ODEX-165 Method of drilling at HW and 2nd site , LDS with UPVC P/L including rising main and delivery connection, Cons. of 200 Cum OHR as per Departmental Design & drawing , providing FHTC and others allied works for PASCHIM CHENGMARI PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000435/2022-2023 | 2862/ALD | 17/01/2023 | 02/04/2025 | M/S SSB CONSTRUCTION CO. | 312.15 | 201.82 | 64.66 | 65
7 | ALIPURDUAR | Kumargram | Alipurduar Division | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000138/2025-2026 | 1347/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | PASCHIM CHENGMARI PIPED WATER SUPPLY SCHEME | SM/13240 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Paschim Chengmari Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000900/2023-2024 | 2484/NMD-II | 11/08/2023 | 02/02/2025 | DILIP MAHATO | 20.14 | 0 | 0 | 100
Total | [13 empty] | 1252.91 | 201.82 | 16.11