## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARUIPARA TG water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000831/2023-2024 | 2412/NMD-II | 10/08/2023 | 09/09/2023 | A.S. ENTERPRISE | 18.42 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Providing balance FHTC for Baruipara PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000211/2023-2024 | 1565/ALD | 24/08/2023 | 23/09/2023 | RAMEN DEY & CO | 4.89 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 1278/ALD | 11/08/2023 | 11/08/2023 | Resource Division | 12.57 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Supply of DI pipe & CI special for Baruipara PWSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000045/2023-2024 | 391/ALD | 19/05/2023 | 18/06/2023 | HARI CONSTRUCTION | 34.33 | 0 | 0 | 90
5 | ALIPURDUAR | Kumargram | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 127/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 8.85 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Material Requisition To Resource Division |  |  | RTOR000044/2024-2025 | 4260/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 13.75 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | New Service Connection Charges for Baruipara pwss PH NO-II |  |  | BILL/00860/2024-2025 | BP-261/24-25 | 09/08/2024 | 09/08/2024 | WBSEDCL | 5.87 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | New Service Connection Charges for Baruipara pwss PH NO-I under NMD-II |  |  | BILL/01181/2024-2025 | BP-326/24-25 | 04/10/2024 | 04/10/2024 | WBSEDCL | 5.85 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr Big dia TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 200 Cum OHR as per Departmental Design and drawing inclu. Soil testing, providing FHTC and others allied works for BARUIPARA PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000429/2022-2023 | 2856/ALD | 17/01/2023 | 28/09/2025 | TAPAN CHANDA | 403.77 | 186.44 | 46.17 | 80
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Solarization of grid connected pumping installation at Different PWSS at Kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001206/2024-2025 | 820/NMD-II | 06/03/2025 | 05/04/2025 | WATER TECH | 29.68 | 0 | 0 | 0
11 | ALIPURDUAR | Kumargram | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
12 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
13 | ALIPURDUAR | Kumargram | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Laying of new UPVC/DI Pipeline for interconnection in the distribution system and bridge/culvert crossing and other allied works in connection with Baruipara PWSS Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000050/2025-2026 | 675/ALD | 21/05/2025 | 19/08/2025 | TAPAN CHANDA | 29.05 | 0 | 0 | 50
14 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000138/2025-2026 | 1347/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
15 | ALIPURDUAR | Kumargram | Alipurduar Division | BARUIPARA AND ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME | SM/13241 | New | Supply of DI specials and CI Jeffy coupling for Baruipara Water Supply Scheme (SM/13241) of Kumargram Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000523/2023-2024 | 842/ALD | 14/03/2024 | 17/09/2024 | MAKALI ENGINEERING CORPORATION | 15.15 | 0 | 0 | 55
Total | [13 empty] | 1409.42 | 186.44 | 13.23