## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHOTO DALDALI water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000843/2023-2024 | 2424/NMD-II | 10/08/2023 | 09/09/2023 | M/S SAJAHAN CHOWDHURY | 21.72 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Providing balance FHTC for Chhoto Daldali PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000208/2023-2024 | 1562/ALD | 23/08/2023 | 22/09/2023 | DAS CONSTRUCTION | 3.35 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Constructions of pump house & Tube well Boring by ODEX-165 Method of drilling at HW site & 2nd site , laying of distribution system with UPVC pipeline , Constructions of 200 Cum OHR as per Departmental Design & drawing , providing FHTC and others allied works for Chuota Daldali PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000508/2022-2023 | 3393/ALD | 16/03/2023 | 12/09/2023 | DAS CONSTRUCTION | 278.2 | 63.09 | 22.68 | 30
4 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1276/ALD | 11/08/2023 |  | Resource Division | 11.58 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 125/ALD | 10/01/2024 |  | Resource Division | 6.17 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Material Requisition To Resource Division |  |  | RTOR000017/2024-2025 | 3951/ALD | 26/11/2024 |  | Resource Division | 6.17 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHOTO DALDALI PWSS PH NO-II |  |  | BILL/00043/2023-2024 | BP-2023-24-44 | 12/05/2023 |  | WBSEDCL | 1.21 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHOTO DALDALI PWSS PH NO-I |  |  | BILL/00044/2023-2024 | BP-2023-24-43 | 12/05/2023 |  | WBSEDCL | 1.21 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Additional Quotation for CHOTO DALDALI PH NO-1 |  |  | BILL/00866/2024-2025 | BP-265/24-25 | 09/08/2024 |  | WBSEDCL | 3.48 | 0 | 0 | null
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Additional Quotation for CHOTO DALDALI PH NO-2 |  |  | BILL/00865/2024-2025 | BP-266/24-25 | 09/08/2024 |  | WBSEDCL | 5.79 | 0 | 0 | null
Total | [13 empty] | 338.86 | 63.09 | 18.62