## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Providing balance FHTC for Chhoto Daldali PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000208/2023-2024 | 1562/ALD | 23/08/2023 | 22/09/2023 | DAS CONSTRUCTION | 3.35 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Constructions of pump house & Tube well Boring by ODEX-165 Method of drilling at HW site & 2nd site , laying of distribution system with UPVC pipeline , Constructions of 200 Cum OHR as per Departmental Design & drawing , providing FHTC and others allied works for Chuota Daldali PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000508/2022-2023 | 3393/ALD | 16/03/2023 | 01/05/2025 | DAS CONSTRUCTION | 278.2 | 126.18 | 45.36 | 65
3 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHOTO DALDALI water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000843/2023-2024 | 2424/NMD-II | 10/08/2023 | 08/05/2025 | M/S SAJAHAN CHOWDHURY | 21.72 | 0 | 0 | 100
4 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1276/ALD | 11/08/2023 | 11/08/2023 | Resource Division | 11.58 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHOTO DALDALI PWSS PH NO-I |  |  | BILL/00044/2023-2024 | BP-2023-24-43 | 12/05/2023 | 12/05/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | QUOTATION FOR NEW SERVICE CONNECTION AT CHOTO DALDALI PWSS PH NO-II |  |  | BILL/00043/2023-2024 | BP-2023-24-44 | 12/05/2023 | 12/05/2023 | WBSEDCL | 1.21 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 125/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 6.17 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Material Requisition To Resource Division |  |  | RTOR000017/2024-2025 | 3951/ALD | 26/11/2024 | 26/11/2024 | Resource Division | 6.17 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Material Requisition To Resource Division |  |  | RTOR000046/2024-2025 | 4262/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 22.34 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Additional Quotation for CHOTO DALDALI PH NO-1 |  |  | BILL/00866/2024-2025 | BP-265/24-25 | 09/08/2024 | 09/08/2024 | WBSEDCL | 3.48 | 0 | 0 | 0
11 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Additional Quotation for CHOTO DALDALI PH NO-2 |  |  | BILL/00865/2024-2025 | BP-266/24-25 | 09/08/2024 | 09/08/2024 | WBSEDCL | 5.79 | 0 | 0 | 0
12 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Solarization of grid connected pumping installation at Different PWSS at Kumargram Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001206/2024-2025 | 820/NMD-II | 06/03/2025 | 05/04/2025 | WATER TECH | 29.68 | 0 | 0 | 0
13 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
14 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
15 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Yard lighting arrangement at Head Work Site for Different PWSS (PASCHIM CHENGMARI and others) under JJM in the BLOCK: Kumargram, DISTRICT: ALIPURDUAR under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000138/2025-2026 | 1347/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 26.74 | 0 | 0 | 0
16 | ALIPURDUAR | Kumargram | Alipurduar Division | CHUOTA DALDALI PIPED WATER SUPPLY SCHEME. | SM/13242 | New | Laying of new UPVC p/l, bridge and culvert crossing, construction of pathway, surface drain and chatal, instalation of paver block, land development along with the other allied works, chhoto Daldali PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000208/2025-2026 | 2350/ALD | 10/11/2025 | 08/02/2026 | DAS CONSTRUCTION | 86.28 | 0 | 0 | 0
Total | [13 empty] | 1304.41 | 126.18 | 9.67