## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Constructions of pump house & Sinking of 250 mm x 200 mm X 150 mtr. Big dia. Tube well at HW site & 2nd site , laying of distribution system with UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil test, providing FHTC and others allied works for Purba Khalisamari PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000557/2022-2023 | 3577/ALD | 27/03/2023 | 17/09/2024 | HARIDAS GHOSH | 438.25 | 320.18 | 73.06 | 72
2 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Supply of CIDF & CISS Pipes and specials for Purba Khalshamari WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000229/2023-2024 | 1604/ALD | 25/08/2023 | 24/09/2023 | HARI CONSTRUCTION | 6.76 | 0 | 0 | 100
3 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Supply of CIDF/CIPE Pipes and Special & CI Jeffy Coupling for Purba Khalishamari Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000481/2023-2024 | 699/ALD | 07/03/2024 | 06/04/2024 | HARI CONSTRUCTION | 15.31 | 7.53 | 49.18 | 70
4 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PURBA KHALISHAMARI water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000793/2023-2024 | 2365/NMD-II | 08/08/2023 | 07/09/2023 | MENAKA ENTERPRISE | 21.73 | 10.59 | 48.74 | 100
5 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 3044/ALD | 08/02/2023 |  | Resource Division | 21.01 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 106/ALD | 10/01/2024 |  | Resource Division | 11.82 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 3613/ALD | 24/10/2024 |  | Resource Division | 7.78 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | NEW SERVICE CONNECTIO CHARGE FOR PURBA KHALISHAMARI W/S/S P/H NO.1 |  |  | BILL/00592/2023-2024 | BP-2023-24-181 | 15/06/2023 |  | WBSEDCL | 1.41 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | PURBA KHALISHAMARI PIPED WATER SUPPLY SCHEME. | SM/13243 | New | NEW SERVICE CONNECTION CHARGE FOR PURBA KHALISHAMARI W/S/S P/H NO.2 |  |  | BILL/00593/2023-2024 | BP-2023-24-182 | 15/06/2023 |  | WBSEDCL | 1.41 | 0 | 0 | 0
Total | [13 empty] | 525.48 | 338.3 | 64.38