## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Nimti Domohini Water Supply Scheme TWNo-I and II under NMD-II,PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001178/2023-2024 | 2909/NMD-II | 31/10/2023 | 30/11/2023 | GURUKRIPA ENTERPRISE | 21.48 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 105/ALD | 10/01/2024 |  | Resource Division | 9.02 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Providing FHTC from existing distribution system as per specification for Nimti Domohani PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000267/2023-2024 | 1885/ALD | 07/09/2023 | 07/10/2023 | DEBAJYOTI SUTRADHAR | 5.22 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | New Service Connection for Nimti Jhora Domohani PWSS P/H NO-I |  |  | BILL/02307/2023-2024 | BP-2023-24-505 | 05/01/2024 |  | WBSEDCL | 5.68 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | New Service Connection for Nimti Jhora Domohani PWSS P/H NO-I |  |  | BILL/02307/2023-2024 | BP-2023-24-505 | 05/01/2024 |  | WBSEDCL | 5.68 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | New Service connection for Nimti Jhora Domohani PWSS, P/H no.-II |  |  | BILL/02410/2023-2024 | BP-2023-24-531 | 11/01/2024 |  | WBSEDCL | 6.47 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Balance portion of 110 mm HDPE/DI pipe laying, boundary wall, pump house, land development for HWS and 1st site and platform for FHTC for Nimti Domohoni PWSS Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000475/2023-2024 | 693/ALD | 07/03/2024 | 05/06/2024 | PINTU SAHA | 79.36 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Supply of DI specials and CI Jeffy coupling for Nimjhora TG Water Supply Scheme(SM/14215) of Kalchini Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000535/2023-2024 | 851/ALD | 14/03/2024 | 13/04/2024 | MANSAROVAR CASTING | 13.34 | 6.67 | 50 | 50
9 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Construction of 2 nos. Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 200 cum OHR as per Departmental Design & drawing, Pump House , Boundary Wall, Path way including soil test, Providing FHTC and other allied works for NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000548/2022-2023 | 3571/ALD | 27/03/2023 | 19/07/2024 | DOOARS CONSTRUCTION COMPANY | 446.14 | 215.85 | 48.38 | 24
10 | ALIPURDUAR | Kalchini | Alipurduar Division | NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME | SM/13244 | New | Supply of DIDF pipes and DI specials and CI Jeffy Coupling for Nimtijhora Domohoni Water Supply Scheme (SM/13244) of Kalchini Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000215/2024-2025 | 2067/ALD | 12/07/2024 | 11/08/2024 | MANSAROVAR CASTING | 9.63 | 0 | 0 | 100
Total | [13 empty] | 602.02 | 222.52 | 36.96