## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL AND SECOND TUBE WELL site including laying distribution system with new HDPE pipeline (Part-B) CONSTRUCTION OF THREE (3) NOS PUMP HOUSES ,providing FHTC and others allied works for PASCHIM SATALI PWSS Under Alipurduar Division PHE DTE. | HQ-A.E |  | ORD/000432/2022-2023 | 2859/ALD | 17/01/2023 | 16/07/2023 | MAHENDRA CHHETRI | 267.57 | 227.68 | 85.09 | 36
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | New Service connection charge for Paschim Satali PWSS P/H No-I. |  |  | BILL/00558/2023-2024 | BP-2023-24-188 | 22/06/2023 |  | WBSEDCL | 1.36 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | New Service connection charge for Paschim Satali PWSS P/H No-II |  |  | BILL/00559/2023-2024 | BP-2023-24-187 | 22/06/2023 |  | WBSEDCL | 1.36 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | New Service connection charge for Paschim Satali PWSS P/H No-III |  |  | BILL/00560/2023-2024 | BP-2023-24-186 | 22/06/2023 |  | WBSEDCL | 1.36 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Constructions of 300 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline (Part-A), RISING MAIN, CONSTRUCTION OF THREE(3) NOS OF BOUNDARY WALL, PATHWAY including soil test, providing FHTC and others allied works for PASCHIM SATALI PWSS Under Alipurduar Division PHE DTE | HQ-A.E | RWS Kalchini Block | ORD/000433/2022-2023 | 2860/ALD | 17/01/2023 | 16/07/2023 | DILIP MAHATO | 497.97 | 365.27 | 73.35 | 74
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Paschim Satali water supply scheme, TW no I, II and III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000026/2023-2024 | 944/NMD-II | 11/05/2023 | 10/06/2023 | M/S BHOWMIK & CO. | 27.59 | 13.52 | 48.99 | 55
7 | ALIPURDUAR | Kalchini | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Balance portion of boundary wall and Gap joint of new HDPE/DI pipeline, and land development of HW Site,1st and 2nd site of Paschim Satali PWSS (Part) Kalchini Block Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000474/2023-2024 | 692/ALD | 07/03/2024 | 05/06/2024 | DILIP MAHATO | 61.82 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Providing FHTC from existing distribution system as per specification for Paschim Satali PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000261/2023-2024 | 1879/ALD | 07/09/2023 | 03/06/2024 | SATYABRATA BHATTACHERJEE | 7.02 | 0 | 0 | 1
9 | ALIPURDUAR | Kalchini | Alipurduar Division | PASCHIM SATALI PIPED WATER SUPPLY SCHEME | SM/13245 | New | Supply of CIDF/CIPE pipes and specials & Sluice Valve for Paschim Satali Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000479/2023-2024 | 697/ALD | 07/03/2024 | 05/06/2024 | SSPR VALVE MANUFACTURING PVT LTD | 18.08 | 9.33 | 51.58 | 80
Total | [13 empty] | 884.13 | 615.79 | 69.65