## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 | New | Boring of TW, Cons. Of Pump House, boundary wall, OHR (300 cum) inclu. Soil investigation works, Laying of rising main, distribution system and providing FHTC for MADHYA KHAIRBARI PWSS under Alipurduar Division PHE DTE. | Alipurduar RWS,Birpara A.E | JUNIOR ENGINEER,RWS Falakata Block | ORD/000553/2022-2023 | 3575/ALD | 27/03/2023 | 17/09/2024 | DILIP MAHATO | 553.32 | 214.31 | 38.73 | 80
2 | ALIPURDUAR | Madarihat | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 | New | Providing FHTC from existing distribution system as per specification for MADHYA KHAIRBARI PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E | JUNIOR ENGINEER,RWS Madarihat - Birpara Block | ORD/000285/2023-2024 | 1992/ALD | 15/09/2023 | 09/09/2024 | DINABANDHU RAY | 16.91 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Madhya Khairbari Water Supply Scheme TW No.- I,II AND III under NMDII, PHE.Dte,APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001141/2023-2024 | 2886/NMD-II | 17/10/2023 | 16/11/2023 | M/S BHOWMIK & CO. | 29.84 | 12.18 | 40.81 | 60
4 | ALIPURDUAR | Madarihat | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 | New | Continuation work order of the work of "Boring of TW, Cons. Of Pump House, boundary wall, OHR (300 cum) inclu. Soil investigation works, Laying of rising main, distribution system and providing FHTC for MADHYA KHAIRBARI PWSS under Alipurduar Division PHE DTE." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/10/2024-EE(ALI_D) SEC-DPHE (Computer No-974292)) | Alipurduar RWS,Birpara A.E | JUNIOR ENGINEER,RWS Falakata Block | ORD/000200/2024-2025 | 1914/ALD | 26/06/2024 | 25/08/2024 | DILIP MAHATO | 26.54 | 13.08 | 49.28 | 90
5 | ALIPURDUAR | Madarihat | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 | New | CONSTRUCTION OF PUMP HOUSE and BOUNDARY WALL FOR ADDITIONAL TUBEWELL and LAYING DISTRIBUTION SYSTEM FOR PROVIDING FHTC AND LAND DEVELOPMENT AT HW SITE and 2ND SITE AT MADHYA KHAIRBARI PWSS WITHIN MADARIHAT-BIRPARA BLOCK. | Birpara A.E | RWS Falakata Block | ORD/000349/2024-2025 | 3419/ALD | 26/09/2024 | 25/11/2024 | MITHUN DAS | 64.12 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 | New | Sinking of Big dia Tube Well (250 x 200 x 150 mm dia) by Modified DTH - ODEX of drilling at Madhya Khairbari PWSS within Madarihat-Birpara Block of RWS SUB-Division under Alipurduar Division, PHE Dte. (SM/13248) | Alipurduar RWS | JUNIOR ENGINEER,RWS Falakata Block | ORD/000237/2024-2025 | 2297/ALD | 07/08/2024 | 06/09/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 18.06 | 0 | 0 | 80
7 | ALIPURDUAR | Madarihat | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 | New | Conceptualization, design and implementing mass awareness generation through Wall writing at 20 nos. villages (Block - Kalchini) by dissemination of awareness generation IEC messages FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation and WASH related issues as per guideline of JJM at Alipurduar district under Alipurduar Division, PHE Dte, Govt. of West Bengal. (SM/13248) | Birpara A.E | JUNIOR ENGINEER | ORD/000496/2023-2024 | 752/ALD | 12/03/2024 | 11/05/2024 | M/S SARKAR & CO | 4.76 | 1.68 | 35.34 | 100
8 | ALIPURDUAR | Madarihat | Alipurduar Division | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 | New | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 115/ALD | 10/01/2024 |  | Resource Division | 15.17 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 | New | NEW SERVICE CONNECTION FOR MADHYA KHAIRBARI PWSS P/H NO I APPLICATION NO 4003065159 |  |  | BILL/01788/2023-2024 | BP-2023-24-367 | 27/09/2023 |  | WBSEDCL | 15.45 | 0 | 0 | 0
10 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 | New | NEW CONNECTION SETRVICE FOR MADHYA KHAIRBARI PWSS P/H NO II APPLICATION NO 4003065166 |  |  | BILL/01789/2023-2024 | BP-2023-24-368 | 27/09/2023 |  | WBSEDCL | 8.34 | 0 | 0 | 0
11 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | MADHYA KHAIRBARI PIPED WATER SUPPLY SCHEME | SM/13248 | New | NEW CONNECTION SETRVICE FOR MADHYA KHAIRBARI PWSS P/H NO III APPLICATION NO 4003065168 |  |  | BILL/01790/2023-2024 | BP-2023-24-369 | 27/09/2023 |  | WBSEDCL | 5.82 | 0 | 0 | 0
Total | [13 empty] | 758.32 | 241.25 | 31.81