## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 3047/ALD | 08/02/2023 |  | Resource Division | 61.86 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1259/ALD | 10/08/2023 |  | Resource Division | 61.75 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Buxa Forest (Raja bhatKhawa) water supply scheme, TW no I of Zone-I and TW-I and II of Zone-II and TW No-I of Zone-III of under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000840/2023-2024 | 2418/NMD-II | 10/08/2023 | 09/09/2023 | M/S P.P ELECTRICALS | 38.78 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Providing balance FHTC from existing distribution system as per specification for BUXA FOREST (RAJABHATKHAWA) PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000321/2023-2024 | 2416/ALD | 09/11/2023 | 08/01/2024 | SHIB RATAN BHOWMIK | 17.96 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Cons. 4 nos Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Cons. of 250 cum OHR as per Departmental Design & drawing, Pump House , Boundary Wall, Path way, Providing FHTC, Soil Testing and other allied works for BUXA FOREST(RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division,Birpara Sub Division | ORD/000176/2023-2024 | 1112/ALD | 28/07/2023 | 24/01/2024 | CAPITAL ENGINEERS | 518.6 | 0 | 0 | 30
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | NEW SERVICE CONNECTION CHARGES FOR BUXA FOREST ZONE-2 PH NO-2 |  |  | BILL/00633/2024-2025 | BP-172/24-25 | 03/07/2024 |  | WBSEDCL | 4.94 | 0 | 0 | null
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | NEW SERVICE CONNECTION CHARGES FOR BUXA FOREST ZONE-2 PH NO-2 |  |  | BILL/00633/2024-2025 | BP-172/24-25 | 03/07/2024 |  | WBSEDCL | 4.94 | 0 | 0 | null
8 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | NEW SERVICE CONNECTION CHARGES FOR BUXA FOREST PWSS ZONE-3 TW NO-1 |  |  | BILL/00634/2024-2025 | BP-173/24-25 | 03/07/2024 |  | WBSEDCL | 5.98 | 0 | 0 | null
9 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | NEW SERVICE CONNECTION CHARGES FOR BUXA FOREST PWSS ZONE-3 TW NO-1 |  |  | BILL/00634/2024-2025 | BP-173/24-25 | 03/07/2024 |  | WBSEDCL | 5.98 | 0 | 0 | null
10 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment of Net Present value( NPV) against proposal no:FP/WB/Others /443394/2023- Cornpensatory levies {demand rote) againstIn-principal (Stage-l) approval of Water Supply Scheme Buxa forest PWSS {Z-Il} Pampu Basty under,Jal Jeelan Mission at Pampu Basti Forest Village - reg"(Annexure- I) |  |  | BILL/00155/2024-2025 | 154/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0 | null
11 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment of Net Present value( NPV) against proposal no:FP/WB/Others /443394/2023- Cornpensatory levies {demand rote) againstIn-principal (Stage-l) approval of Water Supply Scheme Buxa forest PWSS {Z-Il} Pampu Basty under,Jal Jeelan Mission at Pampu Basti Forest Village - reg"(Annexure- I) |  |  | BILL/00155/2024-2025 | 154/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0 | null
12 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment for compensatory afforestation under proposal no FP/WB/others/443394/2023-C0mpenatory Levies(demand note) against In- principal of water supply scheme Buxa forest pwss ( Z-II)Pampu Basty under Jal Jeevan misson at pampu basti forest village - reg as per annexture-2 |  |  | BILL/00156/2024-2025 | 153/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | null
13 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment of Net Present Value ( NPV) against proposal No : FP/WB/Others/ 443397/2023 - Compensatory Levies ( Demand Note) against in- Principal ( Stage-I) approval of water supply Scheme for Buxa Forest PWSS (Z-II) Panijhora under JJM at Panijhora forest village reg |  |  | BILL/00161/2024-2025 | 158/24-25/PFMS | 09/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0 | null
14 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment of Net Present Value ( NPV) against proposal No : FP/WB/Others/ 443397/2023 - Compensatory Levies ( Demand Note) against in- Principal ( Stage-I) approval of water supply Scheme for Buxa Forest PWSS (Z-II) Panijhora under JJM at Panijhora forest village reg |  |  | BILL/00161/2024-2025 | 158/24-25/PFMS | 09/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0 | null
15 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment for boundary demarcation and construction of boundary pillar for the principal ( stage-I) approval for diversion of the forest land of area 0.0232 ha for water supply scheme Buxa forest PWSS(Z-II) Pampu Basty under proposal No :FP/WB/Others/443394/2023 |  |  | BILL/00157/2024-2025 | 152/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0 | null
16 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment for boundary demarcation and construction of boundary pillar for the principal ( stage-I) approval for diversion of the forest land of area 0.0232 ha for water supply scheme Buxa forest PWSS(Z-II) Pampu Basty under proposal No :FP/WB/Others/443394/2023 |  |  | BILL/00157/2024-2025 | 152/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0 | null
17 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment of Net Present value ( NPV) against proposal no : FP/WB/Others/443377/2023- Compensatory levies ( Demand Note ) against In Principal ( Stage-I) approval of water supply scheme for Buxa Forest PWSS ( Z-II)Garo Basty under JJM at Garo Basti Forest Village- reg |  |  | BILL/00158/2024-2025 | 157/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 17.54 | 0 | 0 | null
18 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment of Net Present value ( NPV) against proposal no : FP/WB/Others/443377/2023- Compensatory levies ( Demand Note ) against In Principal ( Stage-I) approval of water supply scheme for Buxa Forest PWSS ( Z-II)Garo Basty under JJM at Garo Basti Forest Village- reg |  |  | BILL/00158/2024-2025 | 157/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 17.54 | 0 | 0 | null
19 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment for compensatory afforestation under proposal no : FP/WB/Others/443377/2023-Compensatory levies ( Demand note) against In - Principal ( Stage-I) approval of Water supply scheme for Buxa Forest PWSS ( Z-II) Garo Basty under jal Jeevan Mission at Garo Basti Forest Village- reg |  |  | BILL/00159/2024-2025 | 155/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | null
20 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment for boundary demarcation and construction of boundary pillar for the principal ( stage-I) approval for diversion of forest land of area 0.157 ha for Buxa forest PwSS ( Z-II ) Garo BastyUnder Proposal No: FP/WB/Others/443377/2023 |  |  | BILL/00160/2024-2025 | 156/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.94 | 0 | 0 | null
21 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Cost of raising and maintenance of the compensatory afforestation for Ca area 0.04 ha ( 100 trees plantation and maintenance for 10 years) against proposed diversion of forrest land for water supply scheme Buxa forest PWSS ( Z-II) panijhora under JJM at panijhora forest Village reg under proposal NO: FP/WB/Others/443397/2023 |  |  | BILL/00162/2024-2025 | 159/24-25/PFMS | 09/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | null
22 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | payment for boundary demarcation and constuction of boundary pillar for the principal ( Stage - I ) approval for diversion of forest land of .0232 ha area for Buxa forest PWSS ( Z-II) Panijhora under JJM at Panijhora forest village - reg under Proposal No: FP/WB/Others /443397/2023 |  |  | BILL/00163/2024-2025 | 160/24-25/PFMS | 09/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0 | null
23 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | payment for boundary demarcation and constuction of boundary pillar for the principal ( Stage - I ) approval for diversion of forest land of .0232 ha area for Buxa forest PWSS ( Z-II) Panijhora under JJM at Panijhora forest village - reg under Proposal No: FP/WB/Others /443397/2023 |  |  | BILL/00163/2024-2025 | 160/24-25/PFMS | 09/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0 | null
24 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment against proposal No : FP/WB/Others /442047/2023-compensatory Levies ( Demand Note)against in- principal ( stage-I) approval of Gravity based WSS for boundary demarcation and construction of boundary pillar for Buxa forest PWSS under JJM at Uttar Poro Forest village -reg |  |  | BILL/00185/2024-2025 | 149/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0 | null
25 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment against proposal No : FP/WB/Others /442047/2023-compensatory Levies ( Demand Note)against in- principal ( stage-I) approval of Gravity based WSS for boundary demarcation and construction of boundary pillar for Buxa forest PWSS under JJM at Uttar Poro Forest village -reg |  |  | BILL/00185/2024-2025 | 149/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0 | null
26 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payement aginst proposal no : FP/WB/Others/ 442047/2023 of Net Present Value of 0.0232 ha ( As per Annexure-1) forest land for diversion for gravity base water supply scheme for Buxa forest PWSS at Uttor Poro under JJM under BTR(WEST) Diivision under WDPO range Poro7Compartment |  |  | BILL/00186/2024-2025 | 150/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0 | null
27 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payement aginst proposal no : FP/WB/Others/ 442047/2023 of Net Present Value of 0.0232 ha ( As per Annexure-1) forest land for diversion for gravity base water supply scheme for Buxa forest PWSS at Uttor Poro under JJM under BTR(WEST) Diivision under WDPO range Poro7Compartment |  |  | BILL/00186/2024-2025 | 150/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0 | null
28 | ALIPURDUAR | Kalchini | Alipurduar Division | BUXA FOREST (RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME | SM/13249 | New | Payment as per annexure -2 against proposal No : FP/WB/Others/442047/2023 for raising and maintenance of the compensatory afforestation ( 100 trees plantation and maintence for 1o years ) agaist proposed diversion of forest land forgravity based piped water supply scheme for Buxa forest PWSS under JJm at Uttar Poro |  |  | BILL/00187/2024-2025 | 151/24-25/PFMS | 08/08/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0 | null
Total | [13 empty] | 783.99 | 0 | 0