## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1474/ALD | 16/08/2023 |  | Resource Division | 38.52 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Providing balance FHTC for Brajerkuthi PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000209/2023-2024 | 1563/ALD | 23/08/2023 | 07/10/2023 | TAPASH KUMAR BHOWMICK | 6.25 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Supply of CIDF & CISS Pipes and specials for Brajerkuti WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000230/2023-2024 | 1602/ALD | 25/08/2023 | 24/09/2023 | TAPASH KUMAR BHOWMICK | 6.76 | 6.76 | 99.96 | 99
4 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | New Service Connection for Brajerkuti PWSS P/HNo-I |  |  | BILL/02311/2023-2024 | BP-2023-24-493 | 21/12/2023 |  | WBSEDCL | 0.71 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | New Service Connection For Brajerkuthi PWSS P/H No-II |  |  | BILL/02312/2023-2024 | BP-2023-24-492 | 21/12/2023 |  | WBSEDCL | 0.71 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | New Service Connection For Brajerkuthi PWSS P/H No-II |  |  | BILL/02312/2023-2024 | BP-2023-24-492 | 21/12/2023 |  | WBSEDCL | 0.71 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 141/ALD | 10/01/2024 |  | Resource Division | 11.38 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Additional quotation For Brajerkuthi P/H No.I |  |  | BILL/02444/2023-2024 | BP-2023-24-560 | 19/01/2024 |  | WBSEDCL | 4.21 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Additional service Connection Charge for Brajerkuthi Ph No.II |  |  | BILL/02445/2023-2024 | BP-2023-24-559 | 19/01/2024 |  | WBSEDCL | 6 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Continuation for the work of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2023 to 31.01.2024) | HQ-A.E |  | ORD/000457/2023-2024 | 2341/ALD | 30/10/2023 | 28/01/2024 | NIRANJAN KIRTANIA | 0.7 | 0 | 0 | 0
11 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2023 to 31.01.2024) | HQ-A.E |  | ORD/000456/2023-2024 | 2340/ALD | 30/10/2023 | 28/01/2024 | NIRANJAN KIRTANIA | 0.5 | 0 | 0 | 0
12 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Laying of new UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Brajerkuti PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000349/2023-2024 | 2601/ALD | 04/12/2023 | 03/03/2024 | TAPASH KUMAR BHOWMICK | 77.06 | 26.26 | 34.08 | 25
13 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. Big dia. TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 200 Cum OHR as per Departmental Design and drawing inclu. Soil testing, providing FHTC and others allied works for Brajerkuthi PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000428/2022-2023 | 2855/ALD | 17/01/2023 | 16/07/2023 | TAPASH KUMAR BHOWMICK | 460.44 | 361.98 | 78.62 | 90
14 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Brajerkuthi water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000801/2023-2024 | 2377/NMD-II | 09/08/2023 | 08/09/2023 | SARKAR ELECTRIC | 18.59 | 0 | 0 | 90
15 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Supply of CIDF/CIPE Pipes and Special & CI Jeffy Coupling for Brajerkuthi Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000484/2023-2024 | 740/ALD | 12/03/2024 | 11/04/2024 | TAPASH KUMAR BHOWMICK | 17.3 | 0 | 0 | 51
16 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | BRAJERKUTHI PIPED WATER SUPPLY SCHEME | SM/13300 | New | Road Restoration of Volka Road against Brajerkuthi PWSS |  |  | BILL/00320/2024-2025 | 189/24-25/PFMS | 10/09/2024 |  | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 10.73 | 0 | 0 | 0
Total | [13 empty] | 660.56 | 395 | 59.8