## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | Constructions of pump house & Sinking of 250 mm x 200 mm X 150 mtr Big dia Tubewel at HW site & 2nd site , laying of distribution system with UPVC pipeline , Constructions of 200 Cum OHR as per Departmental Design & drawing including soil test, providing FHTC and others allied works for Purba Chikliguri PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000431/2022-2023 | 2858/ALD | 17/01/2023 | 11/04/2025 | SOUVIK ROY PALADHI | 481.73 | 324.69 | 67.4 | 65
2 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | Supply of CIDF & CISS Pipes and specials for Purba Chikliguri WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division,RWS Alipurduar - II Block | ORD/000226/2023-2024 | 1603/ALD | 25/08/2023 | 16/02/2025 | SOUVIK ROY PALADHI | 6.76 | 0 | 0 | 100
3 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Purba Chikliguri Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/001180/2023-2024 | 2911/NMD-II | 31/10/2023 | 01/02/2025 | M/S CHANDRANATH MUKHERJEE | 18.82 | 12.02 | 63.85 | 90
4 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 3485/ALD | 23/03/2023 | 23/03/2023 | Resource Division | 11.64 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1473/ALD | 16/08/2023 | 16/08/2023 | Resource Division | 35.41 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | NEW SERVICE CONNECTIO CHARGE FOR PURBA CHIKLIGURI W/S/S P/H NO.1 |  |  | BILL/00594/2023-2024 | BP-2023-24-179 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.41 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | NEW SERVICE CONNECTIO CHARGE FOR PURBA CHIKLIGURI W/S/S P/H NO.2 |  |  | BILL/00595/2023-2024 | BP-2023-24-180 | 15/06/2023 | 15/06/2023 | WBSEDCL | 1.41 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | Laying of new UPVC/DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, land development works, construction of surface drain, pathway, supply of CIDF specials and other allied works in connection with the PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000387/2023-2024 | 198/ALD | 16/01/2024 | 10/04/2025 | SOUVIK ROY PALADHI | 60.36 | 43.39 | 71.89 | 5
9 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | Laying of rising main line with HDPE PN10, horizontal boring by HDD method, bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block along with the others allied works at Madhya Parokata head works site PWSS adjacent to adjacent to Purba Chikliguri WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000486/2023-2024 | 742/ALD | 12/03/2024 | 05/06/2025 | SOUVIK ROY PALADHI | 57.31 | 0 | 0 | 30
10 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | "Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Purba Chikliguri Water Supply Scheme(SM/13301) of Alipurduar-II Block under Alipurduar Division P.H.E. Dte. " | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000525/2023-2024 | 844/ALD | 14/03/2024 | 16/09/2024 | MAKALI ENGINEERING CORPORATION | 15.23 | 15.23 | 100 | 25
11 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 109/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 11.51 | 0 | 0 | 0
12 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | Road Restoration of Volka Road against PURBA CHIKLIGURI PWSS |  |  | BILL/00321/2024-2025 | 190/24-25/PFMS | 10/09/2024 | 10/09/2024 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 8.85 | 0 | 0 | 0
13 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
14 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME | SM/13301 | New | Solarization of grid connected pumping installation at different PWSS at Alipurduar -II block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001205/2024-2025 | 819/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
Total | [13 empty] | 1465.53 | 395.33 | 26.98