## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13302 | New | QUOTATION FOR NEW SERVICE CONNECTION AT DAKSHIN BARAJHAR FOREST PWSS P/H NO. I |  |  | BILL/01451/2023-2024 | BP-2023-24-284 | 21/08/2023 |  | WBSEDCL | 5.32 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13302 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, Laying Of Rising Main, Distribution System and providing FHTC for Dakshin Barajhar Forest PWSS Under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000450/2022-2023 | 2921/ALD | 19/01/2023 | 19/05/2023 | BHAGWATI BHUJEL | 85.2 | 60.05 | 70.48 | 33
3 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13302 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dakhshin Barajhar Forest Water Supply Scheme TW No.-I under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000694/2023-2024 | 2193/NMD-II | 28/07/2023 | 27/08/2023 | MAA TARA ENTERPRISE | 9.85 | 4.58 | 46.55 | 100
4 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | DAKSHIN BARAJHAR FOREST PIPED WATER SUPPLY SCHEME | SM/13302 | New | Laying of DI/HDPE distribution line, land filling at HW site, trial run and allied works at Dakshin Barajhar Forest under Aipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000343/2024-2025 | 3231/ALD | 10/09/2024 | 09/11/2024 | DILIP MAHATO (OPC) PRIVATE LIMITED | 19.62 | 0 | 0 | 0
Total | [13 empty] | 119.99 | 64.63 | 53.86