## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1271/ALD | 11/08/2023 |  | Resource Division | 35.15 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Providing FHTC from existing distribution system as per specification for Atiabari TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000263/2023-2024 | 1881/ALD | 07/09/2023 | 07/10/2023 | SOUVIK ROY PALADHI | 9.84 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1952/ALD | 12/09/2023 |  | Resource Division | 129.38 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | QUOTATION FOR NSC AT ATIABARI PH NO-II |  |  | BILL/01828/2023-2024 | BP-2023-24-326 | 27/09/2023 |  | WBSEDCL | 4.7 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 2785/ALD | 18/12/2023 |  | Resource Division | 11.61 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | New Service Connection for Atiabari T.G PWSS P/H No-I, Kalchini |  |  | BILL/02304/2023-2024 | BP-2023-24-509 | 05/01/2024 |  | WBSEDCL | 5.81 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | New Service Connection for Atiabari T.G PWSS P/H No-I, Kalchini |  |  | BILL/02304/2023-2024 | BP-2023-24-509 | 05/01/2024 |  | WBSEDCL | 5.81 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Supply of CIDF/CIPE pipes and specials and Sluice Valve for Atiabari TG Water Supply Scheme(SM/14092) of Kalchini Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000521/2023-2024 | 840/ALD | 14/03/2024 | 13/04/2024 | MADHAB SAHA | 16.01 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Continuation work order for the work of 'Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil investigation works , 2nos pump house & boundary wall, providing FHTC and others allied works for ATIABARI TEA GARDEN PWSS Under Alipurduar Division PHE DTE." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/9/2024-EE(ALI_D) SEC-DPHE (Computer No-974282)) | HQ-A.E | Alipurduar Sub Division | ORD/000201/2024-2025 | 1915/ALD | 26/06/2024 | 25/08/2024 | SOUVIK ROY PALADHI | 15.17 | 0 | 0 | 0
10 | ALIPURDUAR | Kalchini | Alipurduar Division | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil investigation works , 2nos pump house & boundary wall, providing FHTC and others allied works for ATIABARI TEA GARDEN PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | Alipurduar Sub Division | ORD/000460/2022-2023 | 2981/ALD | 02/02/2023 | 26/07/2024 | SOUVIK ROY PALADHI | 438.53 | 253.05 | 57.7 | 75
11 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | ATIABARI TEA GARDEN PIPED WATER SUPPLY SCHEME. | SM/14092 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Atiabari TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001127/2023-2024 | 2942/NMD-II | 09/11/2023 | 09/12/2023 | M/S ABHISEK ENGINEERING CONCERN | 21.5 | 0 | 0 | 90
Total | [13 empty] | 693.52 | 253.05 | 36.49