## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Providing FHTC from existing distribution system as per specification for Pararpar PWSS PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000275/2023-2024 | 1889/ALD | 07/09/2023 | 07/10/2023 | INDRAYOODH BHOWAL | 8.26 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PARARPAR PWSS P/H NO-I |  |  | BILL/01453/2023-2024 | BP-2023-24-287 | 21/08/2023 | 21/08/2023 | WBSEDCL | 5.89 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | ADDITIONAL QUOTATION FOR APPLICATION NO 4003209532 SITE PARARPAR PWSS ALIPURDUAR. |  |  | BILL/01826/2023-2024 | BP-2023-24-331 | 27/09/2023 | 27/09/2023 | WBSEDCL | 2.44 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PARARPAR PWSS P/H-II |  |  | BILL/01454/2023-2024 | BP-2023-24-288 | 21/08/2023 | 21/08/2023 | WBSEDCL | 5.63 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for PARARPAR water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000682/2023-2024 | 2121/NMD-II | 27/07/2023 | 26/08/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 18.45 | 17.64 | 95.62 | 75
6 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Gap filling and replacing lower dia pipe and FHTC connection at Pararpar PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER,RWS Madarihat - Birpara Block | ORD/000562/2022-2023 | 3505/ALD | 23/03/2023 | 19/09/2023 | TAPASH DAS | 6.38 | 6.35 | 99.46 | 98
7 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Sinking of Big dia Tube Well (250 x 200 mm dia) by R.C. drilling for Aug. of Pararpar PWSS within Alipurduar-I Block of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/14209) | Alipurduar RWS,HQ-A.E | JUNIOR ENGINEER | ORD/000234/2024-2025 | 2294/ALD | 07/08/2024 | 06/09/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 20.72 | 0 | 0 | 100
8 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Material Requisition To Resource Division |  |  | RTOR000038/2024-2025 | 4257/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 36.71 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR (150 cum) including soil testing, Laying Of Rising Main, Distribution System and providing FHTC for Pararpar PWSS Under Alipurduar Division, PHE Dte. (2nd call) | Alipurduar RWS,HQ-A.E | JUNIOR ENGINEER | ORD/000510/2022-2023 | 3397/ALD | 16/03/2023 | 01/09/2025 | SASANKA ROY | 324.42 | 219.59 | 67.69 | 3
10 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | CONSTRUCTION OF PUMP HOUSE & BOUNDARY WALL FOR ADDITIONAL TUBEWELL FOR PROVIDING FHTC AND CONSTRUCTION OF RIVER BANK PROTECTION WALL WITH WIRE CREATE AND FILLING NEAR HWS AT PARARPAR PWSS WITHIN ALIPURDUAR-I BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. | HQ-A.E | JUNIOR ENGINEER | ORD/000025/2025-2026 | 434/ALD | 30/04/2025 | 29/06/2025 | SASANKA ROY | 21 | 0 | 0 | 0
11 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Birpara A.E,HQ-A.E | RWS Falakata Block,RWS Kumargram Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 02/11/2025 | APEX ENGINEERING | 74.36 | 0 | 0 | 65
12 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-I Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | HQ-A.E | RWS Kalchini Block | ORD/000082/2025-2026 | 1050/ALD | 17/06/2025 | 16/08/2025 | MOTI INDUSTRIES | 18.14 | 0 | 0 | 0
13 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Pararpar Water Supply Scheme TW No.-III (Additional) under NMD-II,PHE.Dte,Alipurduar. | HQ-A.E | JUNIOR ENGINEER | ORD/000059/2025-2026 | 787/ALD | 30/05/2025 | 29/06/2025 | SUBODH KUMAR BANIK | 11.09 | 0 | 0 | 0
14 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Solarization of grid connected pumping installation at Different PWSS at APD-I ,APD-II , Falakata Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000132/2025-2026 | 1333/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 27.3 | 0 | 0 | 0
15 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
16 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Gap filling of distribution line, land development and others allied works for augmentation of Pararpar PWSS within APD-I Block under Alipurduar Division, PHE Dte. | HQ-A.E | JUNIOR ENGINEER | ORD/000073/2025-2026 | 971/ALD | 12/06/2025 | 10/09/2025 | SASANKA ROY | 60.73 | 0 | 0 | 0
Total | [13 empty] | 1367.66 | 243.58 | 17.81