## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR (150 cum) including soil testing, Laying Of Rising Main, Distribution System and providing FHTC for Pararpar PWSS Under Alipurduar Division, PHE Dte. (2nd call) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000510/2022-2023 | 3397/ALD | 16/03/2023 | 06/09/2024 | SASANKA ROY | 324.42 | 115.72 | 35.67 | 3
2 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for PARARPAR water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000682/2023-2024 | 2121/NMD-II | 27/07/2023 | 26/08/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 18.45 | 5.88 | 31.85 | 75
3 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Providing FHTC from existing distribution system as per specification for Pararpar PWSS PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | RWS Madarihat - Birpara Block | ORD/000275/2023-2024 | 1889/ALD | 07/09/2023 | 07/10/2023 | INDRAYOODH BHOWAL | 8.26 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Sinking of Big dia Tube Well (250 x 200 mm dia) by R.C. drilling for Aug. of Pararpar PWSS within Alipurduar-I Block of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/14209) | Alipurduar RWS,HQ-A.E | JUNIOR ENGINEER | ORD/000234/2024-2025 | 2294/ALD | 07/08/2024 | 06/09/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 20.72 | 0 | 0 | 100
5 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | Gap filling and replacing lower dia pipe and FHTC connection at Pararpar PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER,RWS Madarihat - Birpara Block | ORD/000562/2022-2023 | 3505/ALD | 23/03/2023 | 19/09/2023 | TAPASH DAS | 6.38 | 6.21 | 97.25 | 98
6 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PARARPAR PWSS P/H-II |  |  | BILL/01454/2023-2024 | BP-2023-24-288 | 21/08/2023 |  | WBSEDCL | 5.63 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PARARPAR PWSS P/H NO-I |  |  | BILL/01453/2023-2024 | BP-2023-24-287 | 21/08/2023 |  | WBSEDCL | 5.89 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | PARARPAR PIPED WATER SUPPLY SCHEME | SM/14209 | New | ADDITIONAL QUOTATION FOR APPLICATION NO 4003209532 SITE PARARPAR PWSS ALIPURDUAR. |  |  | BILL/01826/2023-2024 | BP-2023-24-331 | 27/09/2023 |  | WBSEDCL | 2.44 | 0 | 0 | 0
Total | [13 empty] | 392.19 | 127.81 | 32.59