## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | QUOTATION FOR NSC AT FOSKARDANGA TW NO-II |  |  | BILL/01808/2023-2024 | BP-2023-24-370 | 27/09/2023 | 27/09/2023 | WBSEDCL | 13.41 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | QUOTATION FOR NSC AT FOSKADANGA PH NO-I |  |  | BILL/01782/2023-2024 | BP-2023-24-371 | 27/09/2023 | 27/09/2023 | WBSEDCL | 14.07 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Providing FHTC from existing distribution system as per specification for Foskadanga PWSS PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000272/2023-2024 | 1888/ALD | 07/09/2023 | 07/10/2023 | MADHAB SAHA | 7 | 0 | 0 | 70
4 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 116/ALD | 10/01/2024 | 10/01/2024 | Resource Division | 4.21 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Material Requisition To Resource Division |  |  | RTOR000028/2024-2025 | 3986/ALD | 27/11/2024 | 27/11/2024 | Resource Division | 4.21 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Material Requisition To Resource Division |  |  | RTOR000042/2024-2025 | 4258/ALD | 13/12/2024 | 13/12/2024 | Resource Division | 1.53 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR (100cum) including soil testing, Laying Of Rising Main, Distribution System and providing FHTC for Foskadanga PWSS Under Alipurduar Division, PHE Dte. | Alipurduar RWS,HQ-A.E | JUNIOR ENGINEER | ORD/000549/2022-2023 | 3572/ALD | 27/03/2023 | 02/04/2025 | MADHAB SAHA | 321.67 | 0 | 0 | 10
8 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Laying of new HDPE pipeline for providing FHTC and land filling at Headwork site & 2nd site at Foskadanga PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | JUNIOR ENGINEER | ORD/000030/2025-2026 | 439/ALD | 30/04/2025 | 29/06/2025 | MADHAB SAHA | 52.23 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Solarization of grid connected pumping installation at Different PWSS at Alipurduar-I Block in the dist.of Alipurduar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/001208/2024-2025 | 822/NMD-II | 06/03/2025 | 05/04/2025 | THE BUSINESS ENGINEERS INDIA | 28.94 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of Alipurduar District in West Bengal | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000062/2025-2026 | 1155/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 726.15 | 0 | 0 | 0
11 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for FOKSHADANGA water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000881/2023-2024 | 2457/NMD-II | 11/08/2023 | 17/03/2025 | SAIKAT SINHA | 18.31 | 0 | 0 | 100
Total | [13 empty] | 1191.74 | 0 | 0