## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | QUOTATION FOR NSC AT FOSKADANGA PH NO-I |  |  | BILL/01782/2023-2024 | BP-2023-24-371 | 27/09/2023 |  | WBSEDCL | 14.07 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | QUOTATION FOR NSC AT FOSKARDANGA TW NO-II |  |  | BILL/01808/2023-2024 | BP-2023-24-370 | 27/09/2023 |  | WBSEDCL | 13.41 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 116/ALD | 10/01/2024 |  | Resource Division | 4.21 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Providing FHTC from existing distribution system as per specification for Foskadanga PWSS PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000272/2023-2024 | 1888/ALD | 07/09/2023 | 07/10/2023 | MADHAB SAHA | 7 | 2.39 | 34.11 | 70
5 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for FOKSHADANGA water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000881/2023-2024 | 2457/NMD-II | 11/08/2023 | 10/09/2023 | SAIKAT SINHA | 18.31 | 6.46 | 35.29 | 40
6 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | FOSKADANGA PIPED WATER SUPPLY SCHEME | SM/14210 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR (100cum) including soil testing, Laying Of Rising Main, Distribution System and providing FHTC for Foskadanga PWSS Under Alipurduar Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000549/2022-2023 | 3572/ALD | 27/03/2023 | 18/08/2024 | MADHAB SAHA | 321.67 | 76.88 | 23.9 | 10
Total | [13 empty] | 378.68 | 85.73 | 22.64