## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bhatkhawa TG water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000704/2023-2024 | 2147/NMD-II | 27/07/2023 | 26/08/2023 | MUSTAFI CONCERN | 18.76 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | QUOTATION FOR NSC AT ATIABARI PH NO-II |  |  | BILL/01830/2023-2024 | null | 25/09/2023 |  | WBSEDCL | 7.97 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | QUOTATION FOR NSC AT BHATKHAWA TG PH NO-I |  |  | BILL/01829/2023-2024 | BP-2023-24-325 | 27/09/2023 |  | WBSEDCL | 12.3 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | QUOTATION FOR NSC AT BHATKHAWA TG TW NO-II |  |  | BILL/01848/2023-2024 | BP-2023-24-391 | 06/10/2023 |  | WBSEDCL | 7.97 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 2783/ALD | 18/12/2023 |  | Resource Division | 9.88 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Providing FHTC from existing distribution system as per specification for Bhatkhawa TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Alipurduar Sub Division | ORD/000265/2023-2024 | 1883/ALD | 07/09/2023 | 04/04/2024 | PRANAB GHOSH | 7.16 | 0 | 0 | 100
7 | ALIPURDUAR | Kalchini | Alipurduar Division | BHATKHAWA TEA GARDEN PIPED WATER SUPPLY SCHEME | SM/14211 | New | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new HDPE pipeline , Constructions of 150 Cum OHR as per Departmental Design & drawing , TWO nos pump house & boundary wall, providing FHTC, Soil Investigation work and other allied works for BHATKHAWA TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | Alipurduar Sub Division | ORD/000475/2022-2023 | 3193/ALD | 27/02/2023 | 26/08/2023 | S.G. CONSTRUCTION | 325.36 | 109.18 | 33.56 | 60
Total | [13 empty] | 389.4 | 109.18 | 28.04